# Clause Risk & Compliance Summary

## I. Contract Overview

- Project Title: Not present in contract.

- Solicitation No.: Not present in contract.

- Owner: Not present in contract.

- Contractor: Atlantic Pipe Services LLC (APS)

- Scope: Not present in contract.

- General Risk Level: High – based on cumulative findings across Sections II–VIII indicating significant liability allocation, compliance burdens, and technology/data obligations.

- Bid Model: Not present in contract.

- Notes: FDOT specifications were referenced throughout (2023 edition, as inferred from incorporated references). Contract exhibits elevated substitution liability, strict compliance frameworks (wages, EEO, safety, and cybersecurity), and multiple flow-down risks to subcontractors.

## II. Administrative & Commercial Terms

- Contract Term, Renewal & Extensions

  - Clause Language: Located in Section 01010 (Summary of Work), subsection 1.1.D: "The Contractor shall achieve Substantial Completion of the entire Work within 120 calendar days from the date specified in the Notice to Proceed, and shall achieve Final Completion within 150 calendar days from the date specified in the Notice to Proceed." Located in Section 00700 (General Conditions), Article 12.2: "OWNER may grant extensions of the Contract Times for delays due to unforeseeable causes beyond the control and without the fault or negligence of CONTRACTOR... provided that the CONTRACTOR shall request such extension within 7 days of the occurrence of the event causing the delay."

  - Clause Summary: The contract establishes a fixed duration: 120 days for substantial completion and 150 days for final completion from the Notice to Proceed. It permits extensions only if delays are caused by unforeseeable and uncontrollable events, and only if the contractor submits a request within seven days of the delay event.

  - Risk Triggers Identified: No automatic or mutual renewal clause exists, meaning the contract ends after Final Completion unless extended formally. Delay extension process is tightly constrained by both time (7 days) and discretion of the Owner. No provision for extensions based on contractor or supply chain hardship (e.g., labor/material shortages). Owner discretion on granting extensions may be unevenly applied or subject to interpretation.

  - Flow-Down Obligations: Subcontractors must align their schedules with the prime contractor’s schedule to meet the 120/150-day deadlines. Any request for time extension from a subcontractor must be relayed and supported by the prime contractor promptly. Subcontractor contracts must include back-to-back provisions to preserve entitlement to time extensions.

  - Redline Recommendations: Insert language ensuring equitable time extensions for “force majeure” events, including supply chain disruptions, labor shortages, pandemics, or government-imposed delays. Extend the notice window from 7 to 14 days to allow more practical processing of delay documentation. Add clause requiring Owner’s response to extension requests within a defined period (e.g., 10 business days). Include express recognition that justified subcontractor delays may flow up to the prime contractor.

  - Harmful Language / Policy Conflicts: The “7-day notice” provision is operationally risky and shorter than typical industry standards (often 14–21 days). The absence of objective criteria or timelines for Owner review of extension requests creates ambiguity and potential bias. Lack of mutual renewal or project extension clause limits flexibility for multi-phase or long-lead-time projects.

- Bonding, Surety, & Insurance Obligations

  - Clause Language: 1) “1.2 BONDS AND INSURANCE (Item 1)
A. Payment for bonds and insurance will be made at the lump sum price named in the Bid Schedule. The CONTRACTOR may request payment for this bid item after the Initial Notice to Proceed has been issued.
B. Bonds and Insurance are limited to 3% of the Total Bid Price. Any amount in excess of 3% will be moved to Line Item No. 2, Mobilization, however, the total bid amount will not change.”
2) “1.1 REQUIREMENTS INCLUDED
A. Compile specified guarantees and bonds.
B. Compile specified services and maintenance contracts.
1.3 SUBMITTAL REQUIREMENTS
A. Assemble guarantees, bonds and service and maintenance contracts, executed by each of the respective manufacturers, suppliers, and Subcontractors.
B. Number of original signed copies required: Three each.”
3) “b. Will provide the same guarantees or bonds for the substitution as for the product specified.”

  - Clause Summary: 1) This clause stipulates that bonding and insurance costs are reimbursable at a fixed lump sum and capped at 3% of the total bid. Any amount above this threshold is absorbed into the mobilization line item, maintaining the overall contract price.
2) The contractor must gather and submit executed guarantees, bonds, and service/maintenance contracts from suppliers and subcontractors. Three original signed copies are required.
3) For substituted materials, the contractor affirms equivalent bonding and warranty commitments.

  - Risk Triggers Identified: 1) Ambiguity in whether actual bond/insurance costs exceeding 3% are fully recoverable. Potential undercompensation for contractors in high-risk or specialized insurance markets. Risk of disputes if bid schedule or mobilization line lacks sufficient detail to cover excess.
2) Failure to obtain and compile required bond documentation Lack of verification or noncompliance with bond requirements by subcontractors or manufacturers Incomplete submissions delaying closeout
3) Substitution without adequate bonding Ambiguity in “same guarantees,” especially for custom or novel items

  - Flow-Down Obligations: 1) None specified. Subcontractor bonding and insurance obligations are not addressed in this clause and may need to be covered under separate provisions.
2) Subcontractors and suppliers are required to execute guarantees and bonds, implying a flow-down obligation for compliance and documentation.
3) Subcontractors must provide equal bonding for substituted components as originally specified.

  - Redline Recommendations: 1) Add clarifying language confirming contractor is entitled to actual, reasonable bonding and insurance costs if documented and pre-approved, regardless of 3% cap. Insert obligation for subcontractor bonding and insurance compliance aligned with prime contract obligations.
2) Add a clause specifying bond minimum thresholds and surety qualifications per industry standards. Clarify enforcement timelines and consequences for failure to submit bonds.
3) Define “same guarantees or bonds” quantitatively. Require pre-approval of substituted item sureties.

  - Harmful Language / Policy Conflicts: 1) The 3% cap may create a ceiling that discourages full insurance coverage, especially for complex projects, raising risk exposure. No mention of standard insurance types (e.g., general liability, workers’ compensation, builder’s risk), limits, or additional insured endorsements, which can lead to misaligned risk allocation.
2) None explicitly identified. The clause lacks detail on enforcement and surety qualifications, which may create gaps in protection.
3) The phrase “same guarantees or bonds” is undefined and may lead to insufficient performance protection.

- Retainage, Progress Payments & Final Payment Terms

  - Clause Language: 1) “...the value of WORK done for each activity based on percentage complete for each activity less the amount previously paid for past percentages completed. Summation of all values of each activity less the appropriate percent of retainage shall be the amount payable to the CONTRACTOR...”
2) “Submit Applications for Payment to OWNER in accordance with the schedule... Fill in required information... value of WORK... less retainage...”
3) “Deductions for... reinspection payments... penalties... liquidated damages... uncorrected WORK... to be reflected in the final statement of Contract Sum.”
4) “Final Application for Payment... in accordance with procedures and requirements stated in the Conditions of the Contract.”
5) "CONTRACTOR shall submit the final Application for Payment in accordance with procedures and requirements stated in the Conditions of the Contract." – Section 01770, 1.8 FINAL APPLICATION FOR PAYMENT "OWNER will deduct the amount of such compensation from the final payment to the CONTRACTOR." – Section 01770, 1.5 REINSPECTION FEES "Statement shall reflect all adjustments to the Contract Sum: ... d. Deductions for uncorrected WORK. ... f. Deductions for liquidated damages. ... g. Deductions for reinspection payments." – Section 01770, 1.7 FINAL ADJUSTMENT OF ACCOUNTS

  - Clause Summary: 1) This clause defines how progress payments are calculated. The contractor is paid based on the work completed, minus prior payments and retainage. Retainage is held as a percentage of each progress payment until final completion.
2) Outlines the formal process and documentation required for progress and final payments, including retainage deduction and release procedures.
3) Final payment adjustments include deductions for various failures or penalties. These may reduce final compensation to the contractor.
4) Sets the requirement that final payment must adhere strictly to all prior procedural requirements—documentation, approvals, and accounting reconciliation.
5) These clauses outline the requirements and procedures for submitting final payment applications and adjustments, including the ability of the OWNER to deduct costs for reinspection, uncorrected work, and other contractually permitted offsets from the final payment. There is no express mention of retainage percentage, but payment withholdings are implied through these mechanisms.

  - Risk Triggers Identified: 1) Retainage percentage not defined in this excerpt (may vary by agreement). Payment delays or disputes related to calculation accuracy. Compliance dependency on the contractor’s reporting accuracy.
2) Delay risks if documentation is incomplete or improperly formatted. Owner discretion in approving applications could be a bottleneck.
3) Ambiguous or discretionary deduction language may trigger conflicts. No upper limits or appeal mechanism defined for deductions.
4) Risk of delayed payment if procedural compliance is unclear or inconsistently enforced. Ties final payment to undefined “Conditions of the Contract.”
5) Unbounded discretion for OWNER deductions from final payment. No cap or schedule for release of final payments after deductions. Vague procedures referenced only as "Conditions of the Contract" without specificity. Absence of defined retainage terms suggests risk of hidden withholding.

  - Flow-Down Obligations: 1) Subcontractors must mirror this structure in their own payment expectations and reporting methods. Sub-tier contracts may need to include language about retainage if it’s passed through.
2) Subcontractors must ensure timely submission of payment documentation aligned with prime contractor’s schedule.
3) All subcontractor invoices and final accountings should anticipate potential deductions based on their own performance clauses.
4) Subcontractors need to ensure upstream and downstream compliance to avoid cascading delays.
5) If the CONTRACTOR flows down similar reinspection and deduction terms to subcontractors, consistency must be maintained in timing and documentation standards. Flow-down should also address any final payment timing dependencies explicitly.

  - Redline Recommendations: 1) Specify the exact percentage of retainage (e.g., 0%, 5%) to remove ambiguity. Insert a clear timeline for release of retainage upon project completion or substantial completion.
2) Add a clause ensuring OWNER shall not unreasonably withhold payment approvals. Establish a cure period for correcting incomplete applications before rejection.
3) Cap the amount of allowable deductions or require mutual agreement on adjustments. Define acceptable timelines for dispute resolution before deductions are finalized.
4) Add a clause requiring OWNER to approve/dispute final payment within a defined period (e.g., 10 days). Remove language that allows broad interpretation of “Conditions.”
5) Insert explicit prohibition on arbitrary or excessive OWNER deductions not supported by documented deficiencies. Cap total deduction amount and require itemized notice prior to any deduction from final payment. Define timeline for final payment once final application is submitted. Add a clause specifying that retainage, if any, must be explicitly defined and agreed to in writing with a release trigger.

  - Harmful Language / Policy Conflicts: 1) “Appropriate percent of retainage” is vague; this opens risk for misuse. Could conflict with APS’s standard of 0% retainage if not redlined or negotiated upfront.
2) The clause’s formality requirements can lead to payment delays, conflicting with Net 30 standards unless process is streamlined.
3) Deductions applied without a defined approval/dispute process may conflict with APS payment protection policies.
4) Ambiguity around final payment timing and procedural sufficiency may delay closeout and violate prompt payment standards.
5) The clause “OWNER will deduct the amount... from the final payment” without due process or defined thresholds may conflict with standard fair-payment policies. Lack of defined retainage structure introduces ambiguity and creates a risk of noncompliance with state-level retainage regulations where applicable.

- Pay-When-Paid, Pay-If-Paid, or Owner Payment Contingencies

  - Clause Language: 1) “CONTRACTOR shall pay Subcontractor each progress payment no later than ten (10) days after receipt of payment from the Owner for Subcontractor’s Work. Receipt of payment by the CONTRACTOR from the Owner for the Subcontractor’s Work is a condition precedent to CONTRACTOR’s obligation to pay Subcontractor.”
2) “Summation of all values of each activity less the appropriate percent of retainage shall be the amount payable to the CONTRACTOR, provided that CONTRACTOR has complied with all requirements of the Contract Documents.” — Contract #1 (b), Section 01321, Page 59

  - Clause Summary: 1) This clause establishes a pay-if-paid condition: the contractor is only required to pay the subcontractor after and only if the owner has paid the contractor for the subcontractor’s work. It shifts the risk of non-payment by the owner onto the subcontractor.
2) This clause establishes a conditional payment structure. It states that the contractor’s entitlement to payment is not absolute—it depends on meeting all contractual requirements, and payment is calculated based on approved progress minus retainage. While it doesn’t explicitly invoke "pay-if-paid" language, the phrase “provided that CONTRACTOR has complied with all requirements” introduces a condition precedent, which may indirectly relate to owner funding status or approval cycles that could delay subcontractor payment.

  - Risk Triggers Identified: 1) Owner delays or fails to pay contractor. Subcontractor lacks direct recourse if owner is insolvent. Increased payment timing uncertainty for subcontractor.
2) Conditional payment dependent on undefined “compliance” thresholds Owner discretion over approval of payment Ambiguity regarding timing and linkage to Owner payment Potential downstream delays in subcontractor payment if upstream funds are withheldc

  - Flow-Down Obligations: 1) This clause introduces a flow-down effect whereby subcontractor payment timelines are indirectly tied to the owner’s behavior, despite the subcontractor having no privity with the owner. Sub-subcontractors may also be impacted if similar clauses are used downstream.
2) If the contractor intends to impose similar conditionality on subcontractors (i.e., pay-if-paid terms), such provisions must be explicitly included in subcontract agreements. No automatic flow-down applies without contractual replication.

  - Redline Recommendations: 1) Modify to a pay-when-paid clause with a fixed outer payment deadline (e.g., “in no event later than 45 days from contractor’s receipt of properly submitted invoice”). Strike “condition precedent” and substitute with “payment shall be made within X days regardless of owner payment.”
2) Insert clarifying language separating subcontractor payment obligations from Owner payment status Add a clause affirming that contractor shall pay subcontractors regardless of whether Owner payment has been received, unless pay-if-paid is expressly intended and legally enforceable in the jurisdiction Define “compliance with requirements” with specific and objective criteria

  - Harmful Language / Policy Conflicts: 1) “Condition precedent” raises enforceability risks in jurisdictions where pay-if-paid clauses are restricted or void as against public policy. May conflict with FDOT or state prompt payment laws if applicable.
2) The conditional “provided that” construction may conflict with fair payment policies or prompt payment statutes depending on jurisdiction Absence of clear timing for payment could be leveraged to delay subcontractor compensation Ambiguity creates risk of withholding payment even when substantial performance is complete

- Price Escalation Clauses (Labor, Materials, Fuel, Inflation Adjustments)

  - Clause Language: "Rock excavation shall include removal and disposal of the following... (3) concrete or masonry structures which have been abandoned; and (4) conglomerate deposits which are so firmly cemented that they possess the characteristics of rock as described... Said rock excavation shall be performed by the CONTRACTOR; provided, that should the quantity of rock excavation be affected by any change in the scope of the WORK, an appropriate adjustment of the contract price will be made under a separate bid item if such bid item has been established; otherwise payment will be made in accordance with a negotiated price."

  - Clause Summary: This clause outlines conditions under which the contract price may be adjusted due to material conditions (specifically rock excavation) differing from what was originally anticipated. It allows for either unit pricing if such an item exists or a negotiated adjustment if not.

  - Risk Triggers Identified: Escalation exposure due to unanticipated subsurface rock conditions. Absence of pre-negotiated unit pricing could delay pricing resolution. Potential disputes over what constitutes “rock” without clear quantification in advance.

  - Flow-Down Obligations: If subcontractors are responsible for excavation, prime must ensure that flow-down agreements carry the same conditions for price adjustment in cases of unanticipated rock or similar materials.

  - Redline Recommendations:   Recommend replacing “negotiated price” with “predefined escalation formula or indexed adjustment based on FDOT unit pricing schedules.”   Include requirement for third-party geotechnical verification to qualify as “unanticipated.”

  - Harmful Language / Policy Conflicts: “Negotiated price” introduces ambiguity and delay risk—conflicts with best practices for cost predictability and procurement fairness. No defined escalation trigger or index-based benchmark conflicts with standard escalation clause drafting norms in FDOT-aligned agreements.

- Fuel Price Adjustment / Fuel Cost Caps

  - Clause Language: “The CONTRACTOR shall be responsible for all costs associated with the Work and no additional compensation will be allowed for increased fuel costs unless specifically approved in writing by the OWNER as a change in the Work.”

  - Clause Summary: This clause establishes that the contractor bears the full risk of fuel price escalation, with no default entitlement to reimbursement unless the Owner formally approves it as a change order. No index-based or automatic adjustment mechanism is provided.

  - Risk Triggers Identified: Volatility in fuel markets during the contract period. Absence of an indexed price adjustment formula. Owner discretion as sole relief mechanism may be inconsistently applied.

  - Flow-Down Obligations: The clause implies that subcontractors must also account for fuel price fluctuations in their pricing, as no mechanism for downstream adjustment is referenced.

  - Redline Recommendations: Add a clear fuel price escalation clause referencing an objective index (e.g., U.S. DOE weekly diesel fuel price). Include a threshold (e.g., 10% increase) beyond which adjustments are triggered. Specify adjustment frequency and documentation requirements.

  - Harmful Language / Policy Conflicts: The phrase “no additional compensation will be allowed” is overly rigid and creates financial unpredictability. Reliance on discretionary Owner approval introduces ambiguity and risk of unfair application.

- Change Orders, Scope Adjustments & Modifications

  - Clause Language: 1) “1.10 SCHEDULE REVISIONS - A. Should CONTRACTOR desire to or otherwise be required under the Contract Documents to make modifications or changes in CONTRACTOR’s method of operation, the sequence of WORK or the durations of the activities in the Construction Schedule, CONTRACTOR shall do so in accordance with the requirements of the Contract Documents. The OWNER must approve revisions to the approved Construction Schedule in writing. B. CONTRACTOR shall submit requests for revisions to the Construction Schedule to the OWNER and CONSULTANT, together with written rationale for revisions and description of logic for rescheduling WORK and maintaining the Specific Dates listed in the Contract Documents. Proposed revisions acceptable to the OWNER will be incorporated into next update of Construction Schedule. CONTRACTOR shall pay the OWNER for costs incurred by the OWNER for the revisions.”
2) “1.7 FINAL ADJUSTMENT OF ACCOUNTS - C. ENGINEER will prepare a final Change Order, reflecting approved adjustments to the Contract Sum which were not previously made by Change Orders.”
3) “1.1 REQUIREMENTS INCLUDED - A. Maintain at the site a record copy of: ... 4. Change Orders and other modifications to the Contract.”
4) "ENGINEER will prepare a final Change Order, reflecting approved adjustments to the Contract Sum which were not previously made by Change Orders."
5) “OWNER shall have the sole discretion to agree to or reject such early completion plan by CONTRACTOR. OWNER shall have no duty or obligation to agree to, or to cooperate with CONTRACTOR regarding any early completion plan or proposal by CONTRACTOR and shall not be liable for any damages of CONTRACTOR because of the rejection by OWNER of said plan.”

  - Clause Summary: 1) Contractor-initiated schedule changes must follow formal procedures, including OWNER approval and submission of rationale and logic. Approved changes will be included in future schedule updates, and contractor bears cost of implementing schedule changes.
2) Final reconciliation of contract sum includes a catch-all change order prepared by ENGINEER to incorporate any financial changes not formalized earlier.
3) Contractor must maintain onsite a comprehensive file of change orders and other contract modifications as part of project documentation requirements.
4) This clause assigns the ENGINEER responsibility for drafting a final Change Order to document any approved modifications to the Contract Sum that have not yet been recorded through prior Change Orders.
5) The OWNER retains unilateral discretion over any proposed early completion plans from the CONTRACTOR. There is no obligation on the part of the OWNER to accept, facilitate, or engage in such proposals, and the OWNER disclaims liability for any rejection.

  - Risk Triggers Identified: 1) Informal or undocumented schedule changes Misalignment between revised schedule and contract deliverables OWNER-incurred costs due to contractor-driven revisions.
2) Adjustments not reviewed or contested prior to closeout ENGINEER-driven unilateral changes without contractor input Double-counting or omission due to lack of prior documentation.
3) Loss or misfiling of critical contractual modifications Disputes over version control of executed changes Inability to produce documentation during audit or dispute.
4) Adjustments to Contract Sum not previously documented Lack of clarity or delay in formalizing changes Unilateral authority to define scope/value of final adjustments.
5) Non-objective or non-transparent criteria for proposal acceptance.  Absence of documented evaluation or comparison process for competing project plans. Discretionary decision-making authority without procedural guardrails.

  - Flow-Down Obligations: 1) Yes. Subcontractors affected by revised sequencing or scope must be notified and rescheduled accordingly.
2) Yes. Any financial impact due to late-stage adjustments should flow down to subcontractor closeout reconciliation.
3) Yes. Subcontractors managing documentation should replicate this recordkeeping obligation at their tier.
4) Subcontractors may need to provide documentation of work adjustments or cost impacts to support final adjustments. Flow-down could also include notification obligations and alignment with general contractor's contract accounting.
5) None directly stated; however, subcontractor expectations may need to be aligned to accommodate OWNER's reserved authority over schedule modifications.

  - Redline Recommendations: 1) Clarify scope of what constitutes a “modification,” and define a time window for OWNER/CONSULTANT approval to avoid schedule delays. Also, require OWNER cost justifications in writing if contractor is charged.
2) Include provision requiring contractor's written approval of final change order prior to OWNER’s execution; insert clause allowing challenge of late-stage adjustments within a defined period (e.g., 10 business days).
3) Add language mandating that all change orders be signed and dated, with copies submitted to OWNER within a defined period (e.g., 5 days).
4) Insert requirement that CONTRACTOR shall review and concur with final Change Order before issuance. Require supporting documentation for all adjustments listed. Add obligation that OWNER must also approve the final Change Order for transparency and alignment.
5) Recommend inserting a reference to evaluation criteria or procedural steps to ensure consistency and fairness in proposal reviews. Recommend adding language that clarifies the basis (e.g., cost, schedule impact, quality) on which early completion proposals may be assessed.

  - Harmful Language / Policy Conflicts: 1) Vague terms like “requirements of the Contract Documents” without citation; potential for unilateral OWNER discretion in billing contractor for OWNER-incurred costs.
2) No explicit contractor approval required for financial adjustments—may conflict with internal policy requiring mutual sign-off on cost modifications.
3) None directly, though lack of specificity on update frequency or version tracking may create policy misalignment with ISO 9001/QMS document control.
4) Absence of CONTRACTOR’s concurrence may result in unilateral financial adjustments. No reference to dispute resolution if CONTRACTOR disagrees with final figures. Lack of detailed procedural steps creates ambiguity.
5) The clause presents a risk of arbitrary rejection without recourse, which conflicts with best practices for competitive procurement transparency and equitable treatment of CONTRACTORS.

- Termination for Convenience (Owner/Agency Right to Terminate Without Cause)

  - Clause Language: 1) "The OWNER may, without cause and without prejudice to any other right or remedy, elect to terminate the Contract. In such case, the CONTRACTOR shall be paid (without duplication of any items): a. for completed and acceptable WORK executed in accordance with the Contract Documents prior to the effective date of termination, including fair and reasonable sums for overhead and profit on such WORK; b. for expenses sustained prior to the effective date of termination in performing services and furnishing labor, materials or equipment as required by the Contract Documents in connection with uncompleted WORK, plus fair and reasonable sums for overhead and profit on such expenses; c. for all claims, costs, losses and damages incurred in settlement of terminated subcontracts; and d. for reasonable expenses directly attributable to termination."
2) “The OWNER may at any time and for any reason terminate this Agreement upon giving written notice to the CONTRACTOR. In the event of such termination, the CONTRACTOR shall be paid for all work performed and accepted through the date of termination, including demobilization costs if applicable. The CONTRACTOR shall not be entitled to any further compensation, including for anticipated profits on work not performed.”

  - Clause Summary: 1) The Owner retains the unilateral right to terminate the contract for convenience, i.e., without cause. The contractor is entitled to compensation for completed and in-progress work, including reasonable overhead, profit, and termination-related expenses.
2) This clause grants the OWNER unilateral authority to terminate the contract at any time and for any reason (i.e., at their convenience). The CONTRACTOR is limited to receiving payment for work already completed and approved, plus potential demobilization costs, with no entitlement to future profits or damages.

  - Risk Triggers Identified: 1) Owner-initiated termination without default or breach by Contractor Subjective determination of “fair and reasonable” costs Exposure to broad Owner discretion without dispute mechanism.
2) Termination without cause or contractor breach No requirement for OWNER to justify termination Limited recovery for CONTRACTOR (no expectation damages) Potentially abrupt cessation of project continuity

  - Flow-Down Obligations: 1) Subcontractors must include reciprocal provisions allowing for termination-for-convenience by the Prime Contractor, including detailed handling of cost claims and documentation of incurred expenses.
2) If subcontractors are engaged, the CONTRACTOR must incorporate similar termination provisions into their agreements to mirror OWNER’s right. Failure to flow down could result in CONTRACTOR liability toward subcontractors upon OWNER termination.

  - Redline Recommendations: 1) Insert requirement for advance written notice of termination (e.g., 7–14 days). Add a clause requiring justification or internal approval for use of this termination. Cap or define “reasonable expenses” to reduce ambiguity. Include a mechanism for independent third-party review of cost claims if contested.
2) Add a requirement for OWNER to provide a minimum of 15–30 days advance written notice before termination. Include equitable adjustment provisions to compensate for unrecoverable costs, materials on hand, and subcontractor liabilities. Specify that OWNER shall reimburse reasonable closeout or transition costs.

  - Harmful Language / Policy Conflicts: 1) Unilateral termination rights without a notice period create planning and cost risks. Broad language around compensation (“fair and reasonable”) without defined standards increases potential for dispute. Absence of Contractor input or dispute recourse on termination scope or valuation.
2) Absence of notice requirement allows for immediate termination, which conflicts with fair dealing norms. Waiver of future profits without any balancing compensation may deter contractors from entering similar agreements or pose internal compliance concerns with standard commercial risk tolerances.

- Termination for Cause / Default by Contractor

  - Clause Language: 1) Absence of notice requirement allows for immediate termination, which conflicts with fair dealing norms. Waiver of future profits without any balancing compensation may deter contractors from entering similar agreements or pose internal compliance concerns with standard commercial risk tolerances.
2) "Upon default by the CONTRACTOR, the OWNER may, without prejudice to any other right or remedy, and after giving the CONTRACTOR and the surety seven (7) days written notice, terminate the employment of the CONTRACTOR. The OWNER may then take possession of the site and of all materials, equipment, tools, construction equipment and machinery thereon owned by the CONTRACTOR and may finish the WORK by whatever method the OWNER may deem expedient. If the unpaid balance of the CONTRACT Sum exceeds the costs of finishing the WORK, such excess shall be paid to the CONTRACTOR. If such costs exceed the unpaid balance, the CONTRACTOR shall pay the difference to the OWNER."

  - Clause Summary: 1) The clause grants the Owner broad authority to terminate the contract “for cause,” specifically for contractor default or serious breach. This includes failures in workforce, payments, legal compliance, and insolvency. Upon termination, the Owner may take over the worksite and equipment to complete the work using alternative methods.
2) This clause grants the OWNER the right to terminate the CONTRACTOR for default, with a required seven-day written notice. In the event of such termination, the OWNER can take possession of the job site and any equipment or materials belonging to the CONTRACTOR, and complete the work through any means deemed appropriate. The clause also outlines financial reconciliation following termination, including OWNER reimbursement or CONTRACTOR payment depending on the cost variance.

  - Risk Triggers Identified: 1) Failure to supply skilled labor or proper materials. Non-payment to subcontractors or suppliers. Legal or regulatory violations. Substantial contractual breach. Insolvency or bankruptcy proceedings.
2) Failure of CONTRACTOR to perform contract obligations. CONTRACTOR default or breach. Financial or performance-based inefficiencies requiring OWNER intervention. Short notice for termination (7 days).

  - Flow-Down Obligations: 1) The Contractor must ensure that any subcontractor agreements include corresponding termination-for-cause provisions and that subcontractor performance does not create default triggers under this clause.
2) This clause implies that subcontractors and suppliers may be impacted by the OWNER's possession of equipment and materials. Any downstream entities working under the CONTRACTOR must be prepared for sudden job site reallocation or cessation of work. Flow-down may require mirroring this termination and takeover clause in subcontracts.

  - Redline Recommendations:1)  Add a cure period (e.g., “Contractor shall have 10 business days to cure the default upon written notice from the Owner before termination may proceed”). Add a provision requiring objective evidence of default (e.g., verified nonpayment, documented performance failure). Include mediation or dispute resolution as a precondition to termination.
2) Extend the notice period beyond 7 days to allow for remediation discussions. Require OWNER to substantiate “default” with objective criteria or third-party review. Clarify accounting procedures for “costs of finishing the WORK” to ensure transparency and prevent disputes over cost overruns. Add provisions for equitable resolution of subcontractor obligations following termination.

  - Harmful Language / Policy Conflicts: 1) Clause lacks a defined cure period before termination, which increases contractor risk. Allows unilateral Owner possession of Contractor’s equipment and materials without clear compensation. No limitation on Owner’s discretion in deeming what constitutes a “substantial breach,” exposing Contractor to subjective termination.
2) Ambiguity in "default" definition: No objective threshold for what constitutes default or breach. Broad OWNER discretion: “whatever method…deem expedient” could enable cost-padding or use of inferior resources without accountability. Lack of contractor defense mechanism: No allowance for the CONTRACTOR to dispute the termination or offer cure measures before repossession and takeover.

- Bid Protest Procedures & Claims of Improper Award

  - Clause Language: 1) “No action shall lie against the OWNER or the ENGINEER for the rejection of a bid or proposal or for any award made in good faith and in accordance with applicable law and procedures, nor shall the OWNER or the ENGINEER be liable for any costs incurred by the CONTRACTOR in the preparation or submission of any bid or proposal.”
2) “The OWNER reserves the right to reject any or all BIDS, including without limitation, the right to reject any or all nonconforming, nonresponsive, unbalanced, or conditional BIDS and to reject the BID of any BIDDER if the OWNER believes that it would not be in the best interest of the Project to make an award to that BIDDER.”
3) “No request by CONTRACTOR for a change to the Contract Price or Time under this provision shall be allowed if the CONTRACTOR has not given written notice in strict accordance with these provisions, or if it is made after the date certified by the CONSULTANT as the date of Substantial Completion.”

  - Clause Summary: 1) This clause shields the OWNER and ENGINEER from liability related to the rejection of bids or the award of contracts, provided those actions were done in good faith and per legal procedures. It also disclaims responsibility for proposal preparation costs.
2) Grants the OWNER full discretion to reject bids deemed nonconforming or not in the project’s best interest, without an obligation to justify the decision.
3) This clause creates a rigid limitation on the contractor’s ability to seek any changes to the contract due to perceived award errors or bid process grievances unless they have strictly followed a written notice procedure. It indirectly governs the contractor’s challenge rights by procedural exclusion, and places finality on the CONSULTANT's certification of Substantial Completion.

  - Risk Triggers Identified: 1) Lack of a formal dispute or protest process. Waiver of any contractor recourse against unfair or improper award decisions. No mechanism for contesting bias, irregularity, or procedural defects in selection.
2) Broad discretionary rejection powers with no protest or review mechanism. Potential exposure to favoritism or bias without formal bidder remedy.
3) Lack of formal protest procedure or timeline specific to bid challenges. Broad discretion of the CONSULTANT to determine finality. Strict notice provisions may bar legitimate claims if not meticulously followed. No stated recourse if award process was flawed or unfair.

  - Flow-Down Obligations: 1) None explicitly stated; however, subcontractors would similarly lack standing to challenge award outcomes if the prime cannot.
2) Indirectly affects all lower-tier bidders or partners relying on a fair award process.
3) No explicit flow-down stated; however, subcontractors might also be restricted in challenging project award decisions if this language is mirrored or inherited downstream.

  - Redline Recommendations: 1) Propose inserting a defined bid protest mechanism, including timelines, procedural steps, and recourse options. Add language preserving the CONTRACTOR’s right to challenge material breaches of procurement law.
2) Suggest limiting discretion to objective, clearly defined criteria. Request insertion of a notice-and-comment or appeal period for affected bidders.
3) Introduce a standalone bid protest clause specifying timeframes, procedures, and adjudication forum (e.g., 10 business days from notice of award). Carve out an exception to permit protest or review of errors in award regardless of Substantial Completion date. Require the CONSULTANT to provide justification in writing when denying a bid protest based on timing.

  - Harmful Language / Policy Conflicts: 1) This clause may conflict with internal ethics or compliance programs that support fairness in procurement. The complete waiver of recourse, even in potential bad-faith scenarios masked as “good faith,” is a policy risk.
2) May be in tension with principles of transparency, accountability, and competitive fairness. Could be problematic in jurisdictions with public procurement laws requiring a formal protest opportunity.
3) Phrases such as “no request…shall be allowed” and “in strict accordance” are inflexible and penalize procedural defects rather than substance. Conflicts with public procurement best practices that support transparency and procedural fairness in challenge processes.

- Bid Tabulation, Competition & Award Process Requirements

  - Clause Language: 1) “No separate payment will be made for any item that is not specifically set forth in the Bid Schedule, and all costs therefore shall be included in the prices named in the Bid Schedule for the various appurtenance items of WORK.” “Payment for the various items of the Bid Schedule shall constitute full compensation for CONTRACTOR’s superintendent at the job site full-time during construction…” “Payment shall also include providing the necessary equipment and labor to pothole and verify depths and locations of existing utilities sufficiently ahead of construction to avoid conflicts…” “Payment for all bid items shall constitute full compensation for the complete installation of each bid item including but not limited to excavation, dewatering, backfill and compaction…” “Payment for bonds and insurance will be made at the lump sum price named in the Bid Schedule. The CONTRACTOR may request payment for this bid item after the Initial Notice to Proceed has been issued. Bonds and Insurance are limited to 3% of the Total Bid Price…”

  - Clause Summary: 1) This set of clauses outlines the framework for cost and compensation within the bid tabulation. It specifies that all construction costs must be rolled into the bid prices, including direct and indirect activities, equipment, labor, site preparation, testing, and overhead items like insurance and bonds. It further clarifies the limits of cost attribution and the procedures for claiming payment under specific bid items.

  - Risk Triggers Identified: 1) Absence of itemization may lead to disputes about scope and compensation. “All-inclusive” language can be risky for the contractor if unforeseen conditions arise. The limitation of bond/insurance to 3% could undercompensate depending on market conditions. No clause affirming OWNER’s obligation to review bids for competitiveness or fairness is present.

  - Flow-Down Obligations: 1) All subcontractors must conform to the pricing expectations and limitations embedded in the Bid Schedule. Sub-subcontractors’ activities that relate to compensation must also fall within the parent bid items.

  - Redline Recommendations: 1) Add a clause confirming OWNER’s obligation to conduct a transparent review of submitted bids. Recommend insertion of a provision allowing for equitable adjustment for materially changed site conditions. Expand detail on award criteria and mention if lowest responsive/responsible bidder prevails.

  - Harmful Language / Policy Conflicts: 1) The lack of transparency around the award process may violate procurement integrity best practices if public funds are involved. The "all costs therefore shall be included" language could conflict with corporate risk thresholds if scope is not fully defined.

- Contractor Qualification, Licensing & Certification Requirements

  - Clause Language: 1) “Contractor shall be duly licensed and qualified to perform the Work, and shall maintain all necessary certifications throughout the duration of the Project. Contractor must provide proof of compliance with applicable state and local licensing laws, including evidence of contractor’s and subcontractor’s professional qualifications, relevant trade certifications, and experience documentation, as required under the Scope of Work.”
2) "If your job requires a license (or similar registration), you are required to provide the Company with, automatically as required by Company policy or upon request, valid, unexpired documentation of your license. You must immediately inform your immediate supervisor if any condition related to your licensure changes. Employees required to maintain a license (or similar registration) must renew their licenses as a condition of continued employment. Employees are responsible for renewing their licenses prior to expiration and any associated costs. Employees must provide Human Resources with copies of all renewed licenses prior to expiration of existing license."

  - Clause Summary: 1) This clause establishes that the contractor must hold all required licenses and certifications prior to and during the execution of the work. It includes compliance with local and state requirements and may include trade-specific credentials.
2) Employees whose roles require professional licensing or similar credentials must submit current, valid documentation proactively or upon request. They are responsible for monitoring, renewing, and submitting proof of renewal before expiration. Any changes to licensure status must be reported to supervisors immediately.

  - Risk Triggers Identified: 1) Contractor begins work without proper licensing. Lapsed certifications during project execution. Subcontractors lacking necessary trade credentials. Legal/regulatory noncompliance leading to work stoppages or fines.
2) Noncompliance with local or professional licensing requirements. Lapses in credential validity. Unreported changes in licensure status. Lack of timely renewal or documentation.

  - Flow-Down Obligations: 1) Contractor must ensure all subcontractors and tiered subcontractors are similarly licensed and certified. Flow-down to all entities performing work is required.
2) This clause should flow down to subcontractors, consultants, and any role requiring regulated certifications or licenses—especially those operating under the prime contractor’s oversight or representing the company in regulated environments.

  - Redline Recommendations: 1) Insert a requirement that licenses/certifications be submitted and verified before mobilization. Include language requiring immediate notice to Owner if any required credential lapses or is revoked. Add Owner’s right to terminate or suspend work in the event of non-compliance.
2) Add explicit mention of state and local regulatory compliance, not just internal company policy. Insert a clause requiring third-party contractors to adhere to equivalent licensing documentation standards. Include verification procedures or audit rights by the Company or HR to ensure ongoing compliance.

  - Harmful Language / Policy Conflicts: 1) No harmful or conflicting language was identified, but omission of a verification or enforcement mechanism could weaken enforceability.
2) The clause places full burden on employees without specifying verification or oversight mechanisms by HR. It lacks provisions for temporary suspension or remedial steps if licenses lapse unintentionally, which could increase liability.

- Release Orders, Task Orders & Work Authorization Protocols

  - Clause Language: 1) “Work Authorization: The ENGINEER shall prepare and issue to the CONTRACTOR individual Work Orders authorizing specific construction work to be performed. Each Work Order shall describe the work to be performed, including the location, schedule, and payment terms.”
2) “Execution of work under this Agreement shall be authorized only upon written notice from the OWNER or its authorized representative, detailing scope, compensation, and schedule.”

  - Clause Summary: 1) This clause stipulates that specific tasks under the contract are initiated through separate “Work Orders” issued by the ENGINEER. Each order will contain essential details including scope, location, and financial terms.
2) This clause reinforces that no work shall begin until a written directive is issued by the OWNER or an authorized agent, thereby formalizing task commencement through written notice.

  - Risk Triggers Identified: 1) Delays in issuing Work Orders can halt project momentum. Incomplete or ambiguous orders may lead to disputes over scope or payment. Absence of timeframes for order issuance may cause planning and execution lags.
2) Absence of formal written notice may invalidate work performed. Ambiguity in who qualifies as “authorized representative” could result in unauthorized work execution.

  - Flow-Down Obligations: 1) Subcontractors must not commence task-specific work until a formal Work Order is received. Any delegated work must replicate the same authorization requirement.
2) All downstream service providers (subs or consultants) must also await written authorization before initiating work, ensuring proper control and scope compliance.

  - Redline Recommendations: 1) Add requirement for ENGINEER to issue Work Orders within a defined timeframe (e.g., “within 10 days of milestone completion”). Clarify dispute resolution steps if the CONTRACTOR objects to the terms of a Work Order.
2) Define “authorized representative” clearly within the definitions section. Require all notices to reference project milestones or phases for traceability.

  - Harmful Language / Policy Conflicts: 1) Lacks procedural safeguard for CONTRACTOR to contest or negotiate terms in a Work Order. Payment terms are left vague and may contradict standard procurement policies requiring pre-defined unit rates or fee schedules.
2) No mechanism is stated for CONTRACTOR to request or escalate delays in receiving the authorization. Leaves the potential for retroactive dispute if work is done prior to written confirmation.

- Assignment & Novation Restrictions (Transfer of Contract Rights)

  - Clause Language: Not present in contract

  - Clause Summary: (Not applicable.)

  - Risk Triggers Identified: (Not applicable.)

  - Flow-Down Obligations: (Not applicable.)

  - Redline Recommendations: Since no clause is present, we recommend adding a standard “Assignment & Novation Restrictions” clause structured as follows: Contractor/ Supplier may not assign, novate, or transfer any rights or obligations under this Contract without prior written consent of the Owner/Agency. Consent to not be unreasonably withheld, if desired. Exception for internal transfers to parent or successor entities, subject to notice and eschewing increased burden. Obligor's liability continuation in the event of assignment absent formal novation.

  - Harmful Language / Policy Conflicts: (Not applicable.)

- Audit Rights, Recordkeeping & Document Retention Obligations

  - Clause Language: Not present in contract

  - Clause Summary: (Not applicable.)

  - Risk Triggers Identified: (Not applicable.)

  - Flow-Down Obligations: (Not applicable.)

  - Redline Recommendations: Since the contract lacks any audit or record retention provisions, it is advisable to insert a clause such as: Audit Rights & Recordkeeping Contractor shall maintain all records related to its performance—including financial, operational, correspondence, and regulatory documentation—for at least five (5) years after final payment or resolution of any dispute or audit, whichever occurs later. These records must be made available to the Owner, its representatives, or auditors, upon reasonable notice, during business hours and at no additional cost. All subcontract agreements must include equivalent retention and audit provisions.

  - Harmful Language / Policy Conflicts: (Not applicable.)

- Notice Requirements & Claim Timeframes (Notice to Cure, Delay Notices, Termination Notices, etc.)

  - Clause Language: Not present in contract

  - Clause Summary: (Not applicable.)

  - Risk Triggers Identified: (Not applicable.)

  - Flow-Down Obligations: (Not applicable.)

  - Redline Recommendations: To align with robust contract compliance best practices, consider inserting a clause such as: Notice Requirements & Claim Timeframes
- Contractor must provide written notice of any event that may give rise to a time or monetary claim within 14 calendar days of knowing or receiving notice of the event.
- A detailed claim submission must follow within 21 days of the notice.
- Failure to provide timely notice or supporting documentation shall constitute a waiver of the claim, unless the Owner has been materially prejudiced.
- Curing opportunities: Contractor shall allow Owner 7 days to respond before initiating any formal dispute.
- These requirements flow down to all subcontractors performing related work.

  - Harmful Language / Policy Conflicts: (Not applicable.)

## III. Technical & Performance Terms

- Scope of Work (Work Inclusions, Exclusions & Defined Deliverables)

  - Clause Language: 1) “SECTION 01110 – SUMMARY OF WORK. The WORK to be done under this Contract shall consist of furnishing all labor, materials, equipment, tools, transportation, services, and incidentals necessary to construct and complete in a good, workmanlike, and substantial manner the West Deerfield Capital Improvement Project, Project No. 22014, all as shown on the Drawings and described in the Specifications, together with all appurtenances and incidental items necessary to complete the WORK.”
2) “Provide all labor, materials, necessary equipment and services to complete the Earthwork, as indicated on the DRAWINGS, as specified herein or both, except as for items specifically indicated as 'NIC ITEMS.' Including but not necessarily limited to: Excavation (including demucking), backfilling, filling, grading, compaction, coordination for disposal of excess materials, cutting, proofrolling, filling and grading, moisture content conditioning, removal of unsuitable material, and special construction procedures per geotechnical report. The WORK includes all incidental work necessary to complete the project, regardless of whether or not specifically described”.

  - Clause Summary: 1) This clause establishes the scope of work as requiring the contractor to provide all necessary resources and services for full completion of the West Deerfield project in accordance with contract documents. It clearly defines the inclusive obligation (all labor, materials, equipment, tools, and incidentals).
2) The contract requires the contractor to provide all labor, materials, and equipment to complete the earthwork scope in full, including excavation, grading, compaction, and associated incidental activities. Exclusions are only those specifically marked as "NIC ITEMS."

  - Risk Triggers Identified: 1) Broad “all-inclusive” scope may expose contractor to unanticipated work not explicitly listed. Risk of disputes if exclusions are not expressly stated. Ambiguity regarding “incidentals necessary” could shift unforeseen cost burdens onto contractor.
2) Broad inclusion of "all incidental work necessary" may expand scope beyond defined drawings/specifications. No clear boundary for what constitutes NIC exclusions. Contractor assumes risk for unforeseen site conditions unless explicitly excluded.

  - Flow-Down Obligations: 1) Subcontractors must also provide all labor, materials, and equipment required for their respective scopes. Must ensure all incidental work is accounted for in subcontracts to avoid gaps.
2) Any subcontractor engaged for excavation, grading, or related work must comply fully with the scope requirements, including incidental work obligations.

  - Redline Recommendations: 1) Add explicit scope limitations or exclusions (e.g., hazardous materials abatement, unforeseen utility relocation). Define “incidentals necessary” more narrowly to reduce exposure. Incorporate a requirement for written change orders if owner requests work beyond explicitly listed scope.
2) Narrow the scope by clarifying that incidental work is limited to activities “reasonably inferable” from the drawings and specifications. Require owner-issued written change orders for any additional work outside explicit drawings and specifications. Add explicit exclusions (e.g., hazardous material removal, unexpected subsurface obstructions) to avoid scope creep.

  - Harmful Language / Policy Conflicts: 1) “Furnishing all labor, materials, equipment … and incidentals necessary” is overly broad and risks conflicting with APS policy against open-ended scope obligations. Absence of clear deliverable exclusions increases exposure to scope creep.
2) “All incidental work necessary” is overly broad and inconsistent with APS risk management policy on defined deliverables. Potential conflict with APS redlining guidance requiring precise scoping to avoid undefined liability.

- Performance Schedule, Time for Completion & Critical Path Obligations

  - Clause Language: 1) “Unless otherwise specifically provided in the Contract Documents, CONTRACTOR acknowledges that OWNER has contemplated in OWNER’s planning and approval of the schedule, and in OWNER’s budgeting for professional services, that the WORK will be performed on a 5-day WORK week basis, utilizing a single 8-hour shift per day. OWNER shall have the sole discretion of approving or rejecting a variance in the workweek, number of shifts, or shift length.”
2) “1.8 WORK SCHEDULE. A. Time is of the essence in completing this project. Because time is of the essence the CONTRACTOR shall commit the necessary resources to this project to complete it in a timely manner… The Construction progress will be measured with the construction schedule submitted by the CONTRACTOR. If the ENGINEER determines that the CONTRACTOR does not meet the Critical Path Method (CPM) as specified in Section 01321, ‘Schedules and Reports’ the CONTRACTOR will be required to commit those resources necessary to ensure the completion of the project in a timely manner including working over time, adding other WORK crews, etc. All costs incurred to implement measure to complete the WORK in timely manner will be borne by the CONTRACTOR at no additional cost to the OWNER.”
3) “1.9 COMPUTATION OF CONTRACT TIME. A. It is the CONTRACTOR's responsibility to provide clear and convincing documentation to the ENGINEER as to the effect additional WORK will have with respect to additional contract time extension that may be justified. If additional quantities of WORK can be carried out concurrent with other existing construction activities without disrupting the critical path of the project then no contract time extension will be granted… This contract is a calendar day contract. While the CONTRACTOR may be granted time to suspend WORK operations for vacations or holidays, contract time will not be suspended. During suspensions CONTRACTOR shall be responsible for all maintenance of traffic and liability without additional compensation from the CITY.”
4) “If additional quantities of WORK can be carried out concurrent with other existing construction activities without disrupting the critical path of the project then no contract time extension will be granted. CONTRACTOR is obligated to provide documentation to the ENGINEER if additional elements of WORK affects the critical path of the project. If WORK set forth in the original scope of the project is deleted, the contract time may be reduced. This contract is a calendar day contract. While the CONTRACTOR may be granted time to suspend WORK operations for vacations or holidays, contract time will not be suspended. During suspensions CONTRACTOR shall be responsible for all maintenance of traffic and liability without additional compensation from the CITY.”
5) “The CONTRACTOR shall bring to the conference a copy of the proposed WORK schedule for the approval by the ENGINEER of the proposed methods and manner of executing the WORK including sequences of operation and time schedule. The WORK shall be performed in accordance with such schedule or approved amendments thereto.”

  - Clause Summary: 1) The default schedule for work is a 5-day, single-shift workweek. The OWNER alone has the authority to approve any deviations from this schedule, and the CONTRACTOR must bear any costs related to such changes, including associated consultant or staff adjustments.
2) This clause sets out that time is of the essence and mandates use of the Critical Path Method (CPM) schedule. If the contractor falls behind, it must add crews, overtime, or other resources at its own expense to meet schedule.
3) This provision specifies that contract time runs continuously in calendar days. Time extensions are only granted if the critical path is demonstrably impacted. Contractor must prove entitlement to extensions.
4) This provision establishes the contract as a calendar day contract, strictly defining obligations related to performance schedules. It prohibits contract time extensions unless the critical path is demonstrably affected and documented. It also allows time reduction if scope is deleted, prevents suspension of contract time for holidays/vacations, and holds the contractor responsible for traffic and liability during suspensions.
5) This clause requires the contractor to submit a proposed work schedule at the pre-construction conference, which must be approved by the Engineer. The contractor is bound to execute the work according to the approved schedule or subsequent amendments.

  - Risk Triggers Identified: 1) Unilateral discretion in scheduling without transparent evaluation process Absence of documented or comparative basis for approving alternative work proposals Increased OWNER leverage without procedural checks.
2) Contractor bears full risk of delays regardless of cause if not approved as excusable. ENGINEER has discretion to demand acceleration without compensation. No recognition of external delays unless proven to affect CPM.
3) High burden of proof (“clear and convincing documentation”). Calendar-day contract means no relief for weekends, holidays, or voluntary suspensions. Maintenance obligations during suspensions increase cost exposure.
4) Lack of relief for delays not directly tied to the critical path. Risk of contract time reduction if scope is deleted. Calendar day counting method is inflexible, with no suspension for holidays or vacations. Contractor assumes liability and maintenance during suspensions, creating uncompensated cost risk.
5) Engineer’s approval could limit contractor flexibility. Potential disputes if schedule amendments are delayed or denied. Risk that approval is treated as binding oversight, but liability for delays remains on contractor.

  - Flow-Down Obligations: 1) Subcontractors and suppliers must be informed of and compliant with the default workweek. Any schedule changes must be flowed down with OWNER approval and cost alignment.
2) Subcontractors must also align with CPM schedule to avoid jeopardizing critical path. Any resource increases (overtime, additional crews) will cascade to subcontract costs.
3) Subcontractors must align with calendar-day structure. Any idle time (weekends/holidays) still impacts overall cost structure with no contract relief.
4) Subcontractors must align their work schedules with the overall project’s critical path to avoid disputes about delay liability. Flow-down may include requiring subcontractors to prove impacts to the critical path before requesting time extensions.
5) Contractors must ensure subcontractors adhere to the approved work schedule and coordinate sequencing to avoid schedule deviations.

  - Redline Recommendations: 1) Propose inclusion of documented criteria or submission process for alternative scheduling requests Add obligation for OWNER to respond within a defined timeframe to schedule variance requests.
2) Insert language clarifying that contractor shall not be responsible for delays caused by Owner, Engineer, or third parties. Add clause permitting equitable adjustments for acceleration costs when acceleration is ordered. Reference FDOT Standard Specification (latest applicable year, likely 2021) Section 8-7.3 for excusable, compensable, and non-compensable delay classifications.
3) Insert clause recognizing non-work days (weekends, legal holidays) if no work is permitted by Owner. Adjust burden of proof from “clear and convincing” to “reasonable documentation.” Cross-reference FDOT Specification Section 8-7.3.2 (Excusable Delay) to provide recognized categories.
4) Insert language allowing equitable time extensions for delays beyond contractor’s control (e.g., weather, utility conflicts, permitting). Clarify that scope reductions shall not automatically reduce contract time unless directly affecting the critical path. Add language ensuring suspension of time for City-ordered stoppages or delays beyond contractor’s control.
5) Clarify that Engineer’s approval is for review/coordination purposes only and does not transfer responsibility for schedule performance. Add obligation for Engineer to act reasonably and promptly in approving schedule amendments. Include language permitting contractor adjustments to mitigate unforeseen events without waiting for Engineer’s approval.

  - Harmful Language / Policy Conflicts: 1) Total OWNER discretion without procedural protections poses a risk to fair treatment and operational efficiency. The clause could deter innovative or efficient schedule proposals if approvals are perceived as inconsistent or opaque.
2) Broad “time is of the essence” language + unilateral ENGINEER discretion may conflict with FDOT delay standards which require recognition of excusable delays. No allowance for force majeure or owner-caused delays here (though may appear elsewhere).
3) Burden of proof standard (“clear and convincing”) exceeds normal construction practice. Continuous calendar-day counting may conflict with industry norms and FDOT practices where time suspensions may apply in limited circumstances.
4) “No contract time extension will be granted” unless the critical path is disrupted is overly restrictive. Calendar day contract with no suspension for holidays/vacations is a harsher standard than many industry norms. Liability for maintenance of traffic during suspensions without compensation conflicts with fair allocation of risk.
5) Binding adherence to an Engineer-approved schedule could impair contractor’s flexibility. Risk of owner/engineer control over contractor’s means and methods without corresponding liability.

- Delays of Any Kind (Force Majeure, Acts of God, Weather, Owner-Caused, Unforeseen Events)

  - Clause Language: "No request by CONTRACTOR for a change to the Contract Price or Time under this provision shall be allowed if the CONTRACTOR has not given written notice in strict accordance with these provisions, or if it is made after the date certified by the CONSULTANT as the date of Substantial Completion."

  - Clause Summary: The contract allows for adjustments in price or time due to certain events (potentially including delays), but such requests are strictly conditioned on timely written notice. If the contractor fails to comply with the notice provisions, or submits after Substantial Completion, no relief is permitted.

  - Risk Triggers Identified: Contractor delays caused by unforeseen conditions may not qualify for time/price adjustment without strict notice. Administrative failure to provide written notice could result in forfeiture of legitimate delay claims. Consultant certification of Substantial Completion acts as a hard cutoff, eliminating claims submitted afterward.

  - Flow-Down Obligations: Subcontractors must provide prompt written notice of delays to the prime contractor to preserve claims upstream. Prime contractor must cascade this obligation to ensure lower tiers comply with strict notice deadlines.

  - Redline Recommendations: Insert explicit language defining force majeure, weather events, and owner-caused delays as compensable and excusable. Soften the notice requirement to allow for “substantial compliance” rather than absolute strict compliance. Extend the time to file claims beyond Substantial Completion if the event continues or was not reasonably discoverable.

  - Harmful Language / Policy Conflicts: “Strict accordance” is overly rigid and risks waiving legitimate claims due to minor technical errors. Hard cutoff at Substantial Completion may conflict with state law provisions allowing claims post-completion. Absence of explicit recognition of force majeure or weather delays creates exposure, as the clause relies solely on procedural compliance.

- Suspension of Work, Work Stoppages & Agency Directives

  - Clause Language: "While the CONTRACTOR may be granted time to suspend WORK operations for vacations or holidays, contract time will not be suspended. During suspensions CONTRACTOR shall be responsible for all maintenance of traffic and liability without additional compensation from the CITY."

  - Clause Summary: This clause establishes that suspensions of work for vacations or holidays do not stop the running of contract time. The contractor remains fully responsible for maintaining traffic control and any liabilities during the suspension, without entitlement to additional payment.

  - Risk Triggers Identified: Contractor-initiated suspensions for holidays or vacations. Liability exposure during periods of suspension (e.g., accidents, failures in maintenance of traffic). City refusal to compensate for suspension-related costs.

  - Flow-Down Obligations: Subcontractors and suppliers must be prepared to maintain traffic and liability protections during suspensions, even when no active work is occurring. Flow-down should include suspension risk allocation and responsibility for safety measures.

  - Redline Recommendations: Clarify that suspensions requested by the Owner or Engineer are treated differently and may allow equitable adjustment of time or cost. Add language limiting contractor liability to “reasonable” risks that can be controlled during suspension. Seek to include compensation for extraordinary costs incurred during mandated suspensions (e.g., agency-directed stoppages).

  - Harmful Language / Policy Conflicts: The clause shifts all liability to the contractor during suspensions, even when beyond contractor control (e.g., agency-mandated stoppages). No allowance for equitable relief creates misalignment with standard public contract practices (e.g., FDOT, AIA, ConsensusDocs, which allow adjustments for suspensions directed by the Owner).

- Submittals, Documentation & Approval Requirements

  - Clause Language: 1) “CONTRACTOR shall furnish to the ENGINEER for review, digital copies of each shop drawing submittal. The term ‘Shop Drawing’ as used herein shall be understood to include detail design calculations, shop DRAWINGS, fabrication and installation DRAWINGS, erection DRAWINGS, lists, graphs, catalog sheets, data sheets, and similar items. … Except as may otherwise be indicated herein, the ENGINEER will return prints of each submittal to the CONTRACTOR with its comments noted thereon, within fifteen (15) calendar days following their receipt by the ENGINEER. … The ENGINEER's maximum review period for each submittal, including all resubmittals, will be 15 days per submittal.”
2) “Submit Shop DRAWINGS, Product Data and Samples required by the Contract Documents… CONTRACTOR shall furnish to the ENGINEER for review, digital copies of each shop drawing submittal. The term ‘Shop Drawing’ as used herein shall be understood to include detail design calculations, shop DRAWINGS, fabrication and installation DRAWINGS, erection DRAWINGS, lists, graphs, catalog sheets, data sheets, and similar items.”
3) “All CONTRACTOR shop drawing submittals shall be carefully reviewed by an authorized representative of the CONTRACTOR, prior to submission to the ENGINEER. Each submittal shall be dated, signed, and certified by the CONTRACTOR, as being correct and in strict conformance with the Contract Documents. No consideration for review… will be made for any items which have not been so certified.”

  - Clause Summary: 1) This clause requires the contractor to prepare and submit detailed shop drawings and related technical documents to the engineer for review and approval. It sets procedures for submittals, resubmittals, timelines for engineer review, and the conditions under which fabrication may begin.
2) The contractor must prepare and submit shop drawings, product data, and samples in digital format to the engineer for review. Submittals include a wide range of supporting technical documentation (calculations, catalog sheets, data sheets, etc.).
3) The contractor must internally review and certify each submittal before submission to the engineer. Non-certified submittals will be returned without review, and any delays resulting from this will be the contractor’s responsibility.

  - Risk Triggers Identified: 1) Delays if the contractor submits incomplete or inaccurate submittals. Risk of cost recovery by owner for excessive resubmittals beyond two rounds. Potential project delays if engineer review exceeds 15-day limit. Ambiguity if resubmittals are frequent or submittals are bundled improperly.
2) Delay in submittal review (engineer has 15 days per submittal, extendable to 45 days with resubmittals). Contractor prohibited from fabricating or commencing work requiring submittals until approval is granted. Risk of withheld payments if repeated resubmittals are required beyond the second submission.
3) Risk of delay if submittals are rejected due to missing certification. Full liability placed on the contractor for all errors, misfits, and omissions in submittals, even after engineer review.

  - Flow-Down Obligations: 1) Contractor must ensure that subcontractors and suppliers also prepare and submit accurate shop drawings, product data, and other submittals in compliance with the contract and engineer’s requirements
2) Subcontractors and suppliers must provide their respective documentation to the contractor in time for consolidated submittals. The contractor must ensure all lower-tier parties comply with submittal preparation and content requirements.
3) Subcontractors and suppliers must provide accurate data to enable the contractor to certify compliance.

  - Redline Recommendations: 1) Insert language requiring automatic deemed approval if the engineer does not respond within the 15-day review window. Cap the contractor’s liability for excessive resubmittals by requiring the engineer to justify any rejections in writing. Clarify that fabrication may begin upon “conditional approval” to avoid unnecessary work stoppages. Require electronic submission and tracking to document timelines and avoid disputes.
2) Limit engineer’s review time to a strict maximum without extensions. Insert contractor’s right to proceed with preliminary work if review exceeds stated time. Clarify whether digital submission is the only accepted format to prevent ambiguity.
3) Insert a “good faith reliance” clause where engineer review does provide some shared responsibility for errors overlooked. Narrow contractor’s certification obligation to “best of knowledge” rather than strict correctness.

  - Harmful Language / Policy Conflicts: 1) Clause favors the engineer by giving them broad discretion on requiring resubmittals without accountability for delays. Lack of deemed approval risks indefinite project delays. Owner’s right to withhold payment for excessive engineer review costs shifts risk unfairly to contractor.
2) Clause places all timing risk on the contractor without reciprocal obligation for the engineer’s prompt review beyond 15 days. Payment withholding for excessive submittals may be disproportionate compared to actual project delays.
3) Clause eliminates any protective effect of engineer’s review, shifting all liability to contractor. Potential conflict with fair allocation of risk and industry norms (engineer review typically carries at least limited reliance value).

- Emergency & Contingency Work Obligations

  - Clause Language: “In the event of an emergency affecting the safety of persons or property, the Contractor shall immediately act to prevent threatened damage, injury or loss. Any additional compensation or extension of time claimed by Contractor on account of emergency work shall be determined as provided in the Contract.”

  - Clause Summary: Obligates contractor to act immediately in emergencies to protect people or property, with potential (but not automatic) entitlement to time/cost recovery subject to contract determination.

  - Risk Triggers Identified: Duty triggered without Owner direction. Compensation/time not guaranteed. Broad application risk if “emergency” undefined.

  - Flow-Down Obligations: Subcontractors must be bound to respond promptly to emergencies and permit prime to recover costs from Owner.

  - Redline Recommendations: Limit definition of “emergency” to actual threats to safety/property. Require Owner confirmation in writing for compensability. Insert automatic entitlement to reimbursement for third-party mandated emergency actions (e.g., OSHA, Fire Marshal).

  - Harmful Language / Policy Conflicts: Current language could require unfunded emergency actions. Creates unilateral risk exposure inconsistent with corporate contracting policy.

- Permits, Licensing & Regulatory Approvals for Work

  - Clause Language: 1) “The Contractor shall procure and pay for all permits and licenses necessary for the execution of the Work. Contractor shall comply with all applicable laws, ordinances, rules, and regulations bearing on the performance of the Work.”
2) “The Contractor shall comply with all laws, ordinances, rules, regulations and lawful orders of public authorities applicable to performance of the Work, including securing of permits and licenses. If the Contractor observes that portions of the Contract Documents are at variance with such laws, ordinances, rules and regulations, the Contractor shall promptly notify the Architect and Owner in writing.”
3) “The Contractor shall give all notices and comply with all laws, ordinances, rules, regulations, and lawful orders of any public authority bearing on performance of the Work. The Contractor shall secure and pay for all approvals, easements, assessments, and charges required for construction, use, or occupancy of permanent structures or for permanent changes in existing facilities.”

  - Clause Summary: 1) This clause makes the Contractor responsible for obtaining and paying for all required permits and licenses, and for ensuring compliance with applicable laws and regulations.
2) This clause combines a permitting obligation with a duty to comply with all legal requirements and to notify Owner/Architect if conflicts exist between laws and contract documents.
3) This expands the permitting/licensing duty to include approvals, easements, and assessments tied to project construction and facility use.

  - Risk Triggers Identified: 1) Contractor bears financial responsibility for all permits/licensing costs. Non-compliance with permitting or regulatory requirements could cause delays, penalties, or liability. Risk of regulatory changes during the project shifting unexpected burden to Contractor. 
2) Expands contractor liability by combining permit procurement with broad compliance obligations. Duty to identify legal conflicts places risk on Contractor’s legal interpretation. No clear time or cost relief if conflicts require redesign.
3) Contractor assumes cost and schedule risk for obtaining approvals and easements, which are often Owner responsibilities. Exposure to delay penalties if regulatory agencies are slow in issuing required approvals. Undefined responsibility for long-term facility occupancy approvals.

  - Flow-Down Obligations: 1) This must be flowed down to subcontractors who may require specialty permits or licenses for their work scope.
2) Subcontractors must also be bound to comply with legal and permitting requirements in their scopes.
3) Subcontractors engaged in specialty work (e.g., utility relocations, road closures) must also be held responsible for relevant permits/approvals.

  - Redline Recommendations: 1) Clarify whether Owner will assist in obtaining high-level approvals (e.g., environmental permits, land use approvals). Cap Contractor’s responsibility to “customary construction permits and trade licenses” to avoid absorbing Owner obligations. Add language requiring reimbursement if Owner-directed changes increase permitting costs.
2) Narrow compliance duty to “applicable laws directly governing Contractor’s performance.” Shift responsibility for legal interpretations or conflicts to Owner/Architect. Add Owner obligation to resolve discrepancies between Contract Documents and law.
3) Shift easement and permanent facility approvals to Owner responsibility. Clarify that Contractor is responsible only for temporary construction permits. Require Owner assistance in obtaining permits that require landholder consent or agency-level involvement.

  - Harmful Language / Policy Conflicts: 1) Blanket requirement for all permits could improperly shift Owner’s statutory obligations (e.g., land use or agency-level approvals) onto Contractor. No relief mechanism for permit delays caused by third-party agencies.
2) Risk of implied design responsibility if Contractor is forced to identify/document conflicts between specs and laws. Potential policy conflict if Owner intends to retain full responsibility for regulatory compliance.
3) Uncapped responsibility for permanent facility approvals could create open-ended liability. May conflict with Owner’s statutory duty to obtain property rights and regulatory consents.

- Warranty, Guarantee & Defects Liability Periods

  - Clause Language: 1) “The Contractor warrants to the Owner that all materials and equipment furnished under this Contract shall be new unless otherwise specified, and that all Work shall be of good quality, free from faults and defects, and in conformance with the Contract Documents. The Contractor further warrants that the Work shall remain free from defects for a period of one year from the date of Substantial Completion unless a longer period is specified.”
2) “The Contractor shall promptly correct any Work found not to be in conformance with the Contract Documents, whether observed before or after Substantial Completion and whether or not incorporated in the Project, if notified within the warranty period. The Contractor shall bear all costs of correcting such Work, including additional testing and inspections.”

  - Clause Summary: 1) Contractor guarantees the quality and conformity of the work and materials, warranting them free from defects for at least one year after Substantial Completion (longer if specified).
2) Contractor must correct defective work discovered within the warranty period, at no cost to Owner, including related testing and inspections.

  - Risk Triggers Identified: 1) Contractor responsibility for workmanship beyond turnover. Lack of limitation of liability if defects extend past the defined period. Broad warranty coverage if “good quality” is undefined.
2) Open-ended cost burden for correction, testing, and inspection. No stated cap or proportionality standard. Owner discretion may result in expanded liability.

  - Flow-Down Obligations: 1) Must be flowed down to subcontractors providing materials or labor to ensure defects can be corrected at lower tiers.
2) Must be flowed down to subcontractors and suppliers, as defects may originate in their work.

  - Redline Recommendations: 1) Define “defects” more precisely (e.g., material nonconformance vs. aesthetic issues). Limit warranty period to a fixed duration (e.g., 12 months max) unless extended for specific systems. Clarify exclusions (e.g., ordinary wear and tear, Owner misuse, or lack of maintenance).
2) Limit responsibility to “reasonable costs” directly attributable to Contractor’s work. Exclude defects caused by Owner or third-party misuse. Add process for dispute resolution regarding defect classification.

  - Harmful Language / Policy Conflicts: 1) Overly broad “good quality” standard can impose subjective, non-measurable obligations. Absence of defined remedy procedure (repair, replace, or refund). No cap on liability during defects period.
2) Unlimited liability for correction costs. Extends Contractor risk even after completion and acceptance. No cure period or allowance for negotiation before Owner action.

- Use of APS Tools, Equipment, Materials or Supplies

  - Clause Language: 1) “The Contractor shall be responsible for the proper custody, care, and use of all materials, equipment, and tools furnished by the Owner (APS) for use under this contract. Such items shall remain the property of the Owner, and the Contractor shall be liable for any loss or damage beyond ordinary wear and tear.”
2) “APS-owned tools, materials, and equipment shall be used solely for the performance of work under this contract and shall not be removed from the worksite or used for any other purpose.”

  - Clause Summary: 1) APS (the Owner) provides certain tools, equipment, or materials. The Contractor must safeguard and use them properly. Title remains with APS, and the Contractor bears risk for loss/damage.
2) APS restricts the use of its supplied tools/equipment exclusively to this project scope and prohibits diversion.

  - Risk Triggers Identified: 1) Ambiguity in scope: unclear which items APS will provide. Contractor liability: broad exposure for “any loss or damage” could include theft or unavoidable accidents. No dispute mechanism for contested liability.
2) No explicit remedy if APS tools are unavailable or inadequate. Enforcement ambiguity: does “worksite” include offsite fabrication yards?

  - Flow-Down Obligations: 1) If subcontractors are given access to APS-supplied tools/equipment, Contractor must pass down obligations of custody and liability. Subcontract agreements should require indemnity for damage caused by subs.
2) Subcontractors using APS tools must adhere to same restrictions. Subcontract agreements should require compliance with APS tool-use limitations.

  - Redline Recommendations: 1) Clarify APS’s responsibility for delivery condition and adequacy of supplied tools/materials. Limit Contractor’s liability to negligence or misuse, not all forms of loss/damage. Insert inventory control process (joint inspection upon receipt/return).
2) Add definition of “worksite” to avoid disputes. Provide exceptions for approved offsite use when necessary for completion.

  - Harmful Language / Policy Conflicts: 1) Phrase “liable for any loss or damage beyond ordinary wear and tear” is overly broad without carve-outs for theft, vandalism, or Owner negligence. Conflict risk with standard policy limiting liability for force majeure losses.
2) Restrictive wording could hinder flexibility if APS tools are required at offsite facilities. No balancing obligation on APS to ensure availability of tools in suitable working condition.

- Owner-Supplied Support, Utilities & Site Access Provisions

  - Clause Language: 1) “APS shall provide, at no cost to Contractor, reasonable access to on-site utilities including electrical power, potable water, and sanitary facilities as necessary for performance of the Work.”
2) “APS shall furnish Contractor with sufficient access to the Worksite, including staging and laydown areas, to allow timely performance of the Work.”
3) “Contractor shall use Owner-supplied utilities, support services, and site access solely for the performance of Work under this Contract and shall not divert such resources for other purposes.”

  - Clause Summary: 1) APS must supply essential utilities (electricity, water, sanitation) for contractor use during work.
2) APS is responsible for granting the contractor adequate site access and space for operations.
3) Restricts contractor’s use of APS-provided support solely to project-related activities.

  - Risk Triggers Identified: 1) If utility access is delayed, contractor may face work slowdowns. Ambiguity around what constitutes “reasonable access.”
2) If APS delays access, project schedule could be compromised. “Sufficient access” is vague and subject to dispute.
3) Any incidental use outside of contract scope could be deemed a breach. No guidance on permissible shared or incidental use.

  - Flow-Down Obligations: 1) Contractor must communicate to subcontractors that utilities are supplied by APS and ensure proper use.
2) Contractor must coordinate with subcontractors to ensure they understand access limitations and schedules.
3) Contractor must impose same restrictions on subcontractors.

  - Redline Recommendations: 1) Define “reasonable access” (e.g., specify hours, minimum capacity). Clarify backup utility provisions in case of interruptions.
2) Replace “sufficient access” with measurable commitments (e.g., minimum acreage, defined hours of operation). Add remedies for delays caused by APS’s failure to provide access.
3) Allow incidental or de minimis use (e.g., charging small tools). Add notice-and-cure provision before breach is declared.

  - Harmful Language / Policy Conflicts: 1) Risk of undefined limits could shift cost of alternative supply to contractor.
2) Unclear definitions could enable APS to restrict site access, impacting project progress without liability.
3) Strict restriction with no exceptions increases exposure to claims of misuse.

- Field Ticket, Daily Work Log & Documentation Requirements

  - Clause Language: 1) “The Contractor shall maintain accurate daily logs of work performed, including manpower, equipment utilized, materials incorporated, weather conditions, and any incidents affecting progress. Daily logs shall be made available for inspection by the Owner’s Representative upon request.”
2) “All work performed on a time and materials basis shall be supported by field tickets signed daily by the Owner’s Representative. Field tickets shall detail labor hours, equipment hours, and materials used. Signed field tickets will form the basis for payment.”

  - Clause Summary: 1) Contractor must keep daily logs detailing labor, equipment, materials, and site conditions, and provide them for inspection if requested.
2) Work billed on time and materials must be supported by daily field tickets signed by Owner. Payment is tied to these tickets.

  - Risk Triggers Identified: 1) Failure to maintain or provide logs could result in disputes over payment, schedule, or performance. Owner may use missing/incomplete records to deny claims or enforce penalties.
2) If the Owner’s Representative is not available or refuses to sign, payment exposure exists. Errors or omissions on tickets could invalidate entitlement to payment.

  - Flow-Down Obligations: 1) Subcontractors must be required to maintain daily logs consistent with prime contract requirements and provide them upstream.
2) Subcontractors performing T&M work must provide detailed daily tickets for approval to preserve pass-through payment.

  - Redline Recommendations: 1) Add a clear timeframe for submission (e.g., “logs shall be submitted within 24 hours of each workday”). Clarify that logs are for informational purposes only and not determinative of entitlement to payment.
2) Add a cure provision: “If Owner’s Representative is unavailable, Contractor’s records shall be deemed sufficient unless disputed within X days.” Clarify that lack of signature cannot be used to deny payment where work is otherwise verifiable.

  - Harmful Language / Policy Conflicts: 1) Lack of defined timeframe may expose Contractor to retroactive disputes. “Available upon request” gives Owner discretion that could be used opportunistically.
2) Overly rigid reliance on Owner’s signature shifts risk to Contractor for Owner-caused administrative delays.

- Mobilization & Demobilization Provisions

  - Clause Language: 1) “Mobilization shall include the obtaining of all permits and cost of permits…; moving onto the site of all equipment; temporary buildings, and other construction facilities; and implementing security requirements; all as required for the proper performance and completion of the WORK. Mobilization shall include the following principal items: moving equipment, installing temporary power, water supply, sanitary facilities, permits, insurance, project signage, OSHA notices, safety programs, submittals, audio-visual preconstruction records, field office trailers, storage yard, full-time superintendent, site security and maintenance.”
2) “Payment for mobilization will be made at the lump sum price named in the Bid Schedule. An initial lump sum partial payment of 40%… shall be made upon completion of items #1 thru 9 as outlined in Section 01505. Payment of the remaining 60%… will be made in equal monthly amounts during the duration of the contract time.”
3) “There shall be no special measurement or payment for the WORK under this section, it shall be included in the lump sum price for bid item – Mobilization.”

  - Clause Summary: 1) This clause defines mobilization as a broad set of preparatory activities, including permitting, temporary facilities, safety compliance, and staffing prior to project commencement. It explicitly establishes the contractor’s obligation to have resources in place before substantive work begins.
2) This clause specifies the payment schedule for mobilization: 40% upfront upon completion of early mobilization tasks, and 60% spread over the contract duration.
3) This clause mandates that costs associated with subsurface investigation work are deemed included within the mobilization pay item, with no separate compensation.

  - Risk Triggers Identified: 1) Undefined costs for permits, utilities, and temporary facilities. Broad obligations without clear cost recovery mechanisms. Requirement for superintendent full-time at site from mobilization stage may increase overhead.
2) Delayed recovery of mobilization costs, as 60% is spread across project timeline. Tying payment to specific deliverables (#1–9 tasks) may delay initial funding. No provisions for acceleration or early demobilization.
3) Forces contractor to absorb investigation-related costs under mobilization, creating cost uncertainty. No mechanism for change order or adjustment if investigation scope increases.

  - Flow-Down Obligations: 1) Subcontractors may be indirectly required to comply with site safety programs, permit requirements, and mobilization schedules, though the clause does not expressly mandate subcontractor mobilization terms.
2) Not directly applicable to subcontractors but impacts cash flow available to fund subcontractor mobilization.
3) Subcontractors performing investigation work may be required to accept uncompensated tasks unless explicitly scoped into subcontract.

  - Redline Recommendations: 1) Narrow scope to exclude costs not expressly compensable (e.g., overhead for superintendent). Clarify reimbursement obligations for permits, utilities, and regulatory compliance fees. Add cost recovery carve-outs for unforeseen mobilization requirements.
2) Request larger upfront percentage (e.g., 60% upon completion of early mobilization). Add provision for immediate payment of remaining balance if project is terminated early. Clarify milestone acceptance criteria to avoid disputes.
3) Carve out subsurface investigation as a separately compensable pay item. Add language permitting adjustment if investigation scope materially differs from anticipated.

  - Harmful Language / Policy Conflicts: 1) Overly broad scope creates financial risk by obligating contractor for costs without guaranteed reimbursement. “All permits” and “all security requirements” without qualification may impose compliance obligations beyond intended scope.
2) Current structure burdens contractor with financing mobilization beyond early stages. May conflict with company policy requiring cost recovery for mobilization expenses upfront.
3) Bundling costs within mobilization undermines transparency and prevents cost recovery. Contradicts policy of ensuring direct compensation for specialized technical work.

- Utility Coordination, Locate Risk & Conflict Avoidance

  - Clause Language: 1) “All utility lines, both underground and overhead, shall be located and protected prior to commencing work. The contractor is responsible for coordinating with each utility owner to prevent service disruptions and shall immediately notify the Engineer of any conflicts. Where relocation of existing utilities is necessary, the contractor shall coordinate schedules and responsibilities with utility owners.”
2) “The existence and location of utilities (overhead, above ground and underground) shall be thoroughly investigated and verified by the CONTRACTOR before the WORK begins in the area of said utilities. The CONTRACTOR shall exercise care in digging and working so as not to damage utilities or endanger the safety and lives of people. Should overhead, above ground or underground obstructions be encountered which interfere with the WORK, the ENGINEER shall be consulted in order for a decision to be made on the relocation of the WORK to clear such obstruction. The CONTRACTOR shall be responsible for the immediate repair of any damage to utilities caused by the WORK.”
3) “In the event that the CONTRACTOR damages any existing utility lines that are not indicated or the locations of which are not made known to the CONTRACTOR by Sunshine State One Call Center prior to excavation, a written report thereof shall be made immediately to the ENGINEER. If directed by the ENGINEER, repairs shall be made by the CONTRACTOR under the provisions for changes and extra WORK contained in the General Conditions of the Contract. The CONTRACTOR shall be responsible for all repair or relocation costs for any failure by the CONTRACTOR to contact appropriate utilities for locations prior to digging.”
4) “The CONTRACTOR shall notify each utility company involved at least thirty (30) days prior to the start of construction to arrange for positive underground location, relocation or support of its utility where that utility may be in conflict with or endangered by the proposed construction. Relocation of water mains or other utilities for the convenience of the CONTRACTOR shall be paid for by the CONTRACTOR. All charges by utility companies for temporary support of its utilities shall be paid for by the CONTRACTOR. All costs of permanent utility relocations to avoid conflict shall be the responsibility of the CONTRACTOR and the utility company involved.”

  - Clause Summary: 1) This clause places on the contractor the duty to: Locate all utilities before starting work. Coordinate with utility owners to avoid damage or conflict. Notify the Engineer of conflicts. Manage scheduling if relocation is required. 
2) Contractor must locate and verify all utilities before starting work, avoid damage, and consult with the Engineer when conflicts arise. Contractor bears repair responsibility.
3) Contractor must report damage to unknown utilities. If proper One Call notice was given, extra work provisions may apply. Otherwise, contractor bears full responsibility.
4) Contractor must provide advance notice to utilities and is responsible for relocation costs if for their convenience; permanent relocations split with utility owners.

  - Risk Triggers Identified: 1) Failure to identify buried or overhead utilities before excavation. Unclear allocation of responsibility for relocation delays or costs. Service interruptions leading to third-party claims. Ambiguity if utility owners refuse or delay relocation. 
2) Failure to locate/verify utilities before excavation. Utility damage during construction. Uncoordinated relocation decisions. 
3) Failure to notify One Call prior to excavation. Utility damage where records were incomplete but notice not properly given. 
4) Failure to provide timely notice (30 days). Ambiguity in cost-sharing for permanent relocations. Financial exposure for temporary supports.

  - Flow-Down Obligations: 1) Contractor must ensure subcontractors and any specialty crews also: Perform locates before beginning work. Avoid interfering with utility easements. Notify APS and the Engineer of conflicts discovered during subcontracted work. 
2) Subcontractors performing excavation must comply with utility verification and protection protocols.
3) Excavation subcontractors must follow One Call notification procedures.
4) Utility coordination and cost responsibility terms must flow to subcontractors.

  - Redline Recommendations: 1) Clarify cost responsibility for delays caused by utility owners. Add requirement for documented utility coordination meetings before major phases. Insert indemnity carve-out if delays are caused solely by utility owners. Specify timeframes for notice of conflicts and required Engineer response. 
2) Add requirement for formal coordination with utility owners, not just the Engineer. Clarify cost responsibility for relocation when utilities are inaccurately mapped. 
3) Clarify that responsibility shifts if utilities fail to mark or provide accurate information after proper notice. Include explicit cost-sharing mechanism when damages occur despite compliance. 
4) Clarify allocation of relocation costs when conflicts are not caused by contractor. Reduce notice requirement to align with statutory One Call deadlines (often shorter than 30 days).

  - Harmful Language / Policy Conflicts: 1) Broad contractor responsibility could expose APS to costs/damages outside its control. No explicit allocation of responsibility for “betterment” utility upgrades during relocation. Potential conflict with Florida law requiring utility owners to bear certain relocation costs. 
2) Language places unilateral repair costs on Contractor even if utility records are inaccurate. No clear process for equitable sharing of relocation costs.
3) Clause still leans heavily against contractor even in cases of incomplete records, unless a very strict One Call notice procedure is followed.
4) Imposes relocation costs without clear definition of “convenience of the Contractor.” May create disputes with utility owners.

- Delivery Deadlines, Milestone Dates, Substantial & Final Completion Standards

  - Clause Language: 1) “When CONTRACTOR considers the WORK is substantially complete, the CONTRACTOR shall submit to ENGINEER: (1) a written notice that the WORK, or designated portion thereof, is substantially complete; (2) a list of items to be completed or corrected; and (3) final as-builts per requirements. Within a reasonable time after receipt, OWNER and ENGINEER will inspect to determine the status of completion. If not substantially complete, ENGINEER will notify CONTRACTOR in writing. When ENGINEER concurs, a Certificate of Substantial Completion shall be prepared and submitted for OWNER and CONTRACTOR acceptance.”
2) “On completion of the WORK, the CONTRACTOR shall submit written certification that: (1) Contract Documents have been reviewed; (2) WORK has been inspected for compliance; (3) WORK has been completed in accordance with Contract Documents; (4) Equipment and systems have been tested in the presence of the ENGINEER and are operational; and (5) WORK is ready for final inspection. ENGINEER will then make an inspection. If incomplete or defective, CONTRACTOR must remedy deficiencies and resubmit certification. When ENGINEER finds the WORK acceptable, closeout submittals will be requested.”
3) “Should OWNER or ENGINEER perform reinspections due to failure of the WORK to comply with the claims of status of completion made by the CONTRACTOR, the CONTRACTOR will compensate OWNER or ENGINEER for such additional services, and/or OWNER will deduct the amount from the final payment.”
4) “Time is of the essence in the performance of this Contract. The WORK shall be commenced on the date stated in the Notice to Proceed and shall be substantially completed within the time specified in the Agreement. Final completion shall be achieved within thirty (30) calendar days after substantial completion, subject to adjustments as provided in the Contract Documents.”
5) “The ENGINEER may, at OWNER’s request, determine milestone dates for critical activities within the construction schedule. CONTRACTOR shall comply with such milestone dates as binding obligations under the Contract, and failure to do so shall be treated as a failure to meet substantial completion requirements.”

  - Clause Summary: 1) Defines the process for declaring Substantial Completion, including contractor notice, engineer inspection, correction of deficiencies, and issuance of a Certificate of Substantial Completion.
2) Outlines contractor’s obligations for final completion, certification, and engineer’s inspection, with requirements to correct deficiencies prior to acceptance.
3) Allows OWNER to recover costs if contractor’s certification of completion is found inaccurate, requiring reinspection.
4) Sets delivery deadlines and enforces time-of-the-essence for both substantial and final completion, establishing a default 30-day window for final completion post-substantial completion.
5) Authorizes OWNER/ENGINEER to impose additional milestone dates, treating them as enforceable obligations tied to substantial completion.

  - Risk Triggers Identified: 1) Contractor prematurely declaring substantial completion. Engineer/owner dispute over completion status. Delays in correction of deficiencies impacting project timelines. 
2) Contractor’s failure to deliver complete closeout documentation. Inadequate or failed testing of equipment prior to certification. Engineer repeatedly rejecting “final completion” causing delay in payment.
 3) Broad discretion for OWNER/ENGINEER to charge reinspection costs. Contractor submitting premature or incorrect certifications. 
4) Delays in substantial completion automatically impact final completion deadline. Lack of clarity on permissible “adjustments” could cause disputes. Potential exposure to liquidated damages if deadlines are not met. 
5) Unilateral imposition of milestone dates after contract execution. Contractor bears risk of delays caused by OWNER-directed milestone shifts.

  - Flow-Down Obligations: 1) Contractor must enforce the same completion standards and notice requirements on subcontractors for portions of work assigned to them.
2) Subcontractors providing equipment/systems must deliver test results and warranties aligned with contractor’s final certification.
3) Subcontractors must ensure accuracy of their work certifications to avoid triggering contractor liability for reinspection costs.
4) Contractor must enforce timely performance from subcontractors to meet both substantial and final deadlines.
5) Contractor must ensure subcontractors are bound to new milestone requirements.

  - Redline Recommendations: 1) Add clear timeline for OWNER/ENGINEER inspection after contractor’s notice. Insert consequences (liquidated damages or withholding) for repeated false declarations of substantial completion. Clarify acceptable “reasonable time” in measurable days. 
2) Add explicit timeframe for ENGINEER’s review (e.g., within 10 days). Insert provision requiring OWNER’s prompt written acknowledgment of final acceptance. Clarify contractor’s entitlement to final payment timeline upon certification. 
3) Limit OWNER’s ability to deduct costs to instances of contractor negligence or repeated false certifications. Require notice and documentation of reinspection costs before deduction. 
4) Define the permissible “adjustments” (extensions, excusable delays, or compensable events). Clarify that deadlines will be extended for OWNER-caused delays or force majeure. 
5) Require milestone dates to be agreed in writing at contract execution, not unilaterally imposed later. Insert provision limiting milestone changes to mutually agreed schedule updates.

  - Harmful Language / Policy Conflicts: 1) “Reasonable time” is vague and risks open-ended inspection delays. No express remedy for disputes between OWNER and CONTRACTOR regarding substantial completion. 
2) Repeated “reinspection” obligations shift costs to contractor, potentially excessive without limit. Risk of indefinite delay in final acceptance without OWNER accountability. 
3) No cap on reinspection charges, creating open-ended financial exposure. No reciprocal obligation for OWNER if delays or reinspection result from their failure to provide access or approvals. 
4) “Time is of the essence” language heightens exposure to termination/liquidated damages without OWNER accountability. No reciprocal obligation for OWNER to provide timely access, approvals, or materials. 
5) Creates imbalance by permitting OWNER to redefine “substantial completion” criteria mid-project. Risk of expanded contractor liability for noncompliance with unnegotiated deadlines.

- Punch List, Closeout Procedures & Acceptance of Work

  - Clause Language: 1) “Upon Substantial Completion, the Contractor shall prepare and submit to the ENGINEER a punch list of items to be completed or corrected. The ENGINEER shall review, amend if necessary, and provide the punch list to the Contractor. The Contractor shall promptly complete all punch list items to the satisfaction of the OWNER and ENGINEER as a condition precedent to Final Completion.”
2) “Final Acceptance of the Work shall not occur until all punch list items have been completed, closeout documents submitted, warranties delivered, and OWNER has issued a Certificate of Final Completion.”
3) “Submission of closeout documents, including as-builts, operation manuals, and warranties, is a condition precedent to final payment. Failure to deliver such documents shall entitle OWNER to withhold payment until satisfied.”

  - Clause Summary: 1) Contractor must create a punch list at substantial completion, which the ENGINEER/OWNER will review and finalize. Completion of punch list items is required before Final Completion is certified.
2) Final acceptance is expressly conditioned on completion of all outstanding items, submittal of required documents, and OWNER’s issuance of completion certificate.
3) Contractor must provide specified documentation before receiving final payment.

  - Risk Triggers Identified: 1) Potential OWNER/ENGINEER unilateral control in modifying punch list. Undefined timeframe for Contractor to complete punch list items. Risk of disputes if OWNER expands punch list beyond agreed work. 
2) OWNER’s broad discretion in determining whether punch list items are complete. No default acceptance timeline; Contractor may face indefinite obligations. Payment exposure if acceptance withheld without clear reason. 
3) OWNER’s right to withhold payment for incomplete documentation. No cure period for Contractor to resolve deficiencies. Exposure if subcontractors delay submission.

  - Flow-Down Obligations: 1) Contractor must flow down punch list obligations to subcontractors to ensure timely correction and final acceptance.
2) Contractor must ensure subcontractors provide all required warranties, as-built documentation, and corrective work to achieve acceptance.
3) Contractor must obligate subcontractors to submit documentation timely (manuals, warranties, as-builts).

  - Redline Recommendations: 1) Add a specified time period (e.g., 30 days) for completion of punch list items. Limit OWNER/ENGINEER’s right to amend the punch list to avoid scope creep. Provide for mutual agreement on punch list before binding.
2) Insert automatic deemed acceptance if OWNER does not issue certificate within a reasonable timeframe (e.g., 15 days after completion notice). Define what constitutes “minor” vs. “major” punch list items to prevent disputes. 
3) Add a cure period (e.g., 10 business days) for incomplete submissions. Limit OWNER’s withholding to the value of missing documentation rather than total final payment.

  - Harmful Language / Policy Conflicts: 1) One-sided OWNER/ENGINEER discretion may lead to unreasonable obligations. Lack of defined deadlines increases uncertainty and may delay final payment. 
2) Indefinite OWNER discretion risks unfair delay of final acceptance and payment. Burdensome requirements without reciprocal OWNER obligations conflict with balanced risk allocation standards. 
3) Creates disproportionate leverage for OWNER if entire final payment is withheld.

- Worksite Coordination, Access Restrictions & Sequencing Obligations

  - Clause Language: 1) “The Contractor shall coordinate its work with that of other contractors, subcontractors, and the Owner’s operations to avoid conflicts, delays, or interference. The Contractor shall comply with all site access requirements established by the Owner, including restricted zones and scheduling constraints.”
2) “Contractor shall plan and sequence its work so as not to unreasonably interfere with the operations of the Owner or occupants of the facility. Access to certain areas will be limited to specified hours as directed by the Owner.”

  - Clause Summary: 1) This clause requires the Contractor to ensure proper coordination with all parties on site, comply with access restrictions, and sequence activities to minimize disruption.
2)  Obligates Contractor to sequence work carefully to avoid disruption to Owner operations, with explicit recognition that access to some areas will be restricted to Owner-controlled schedules.

  - Risk Triggers Identified: 1) Failure to coordinate with other contractors could lead to project delays. Owner-imposed access restrictions may limit productivity. Ambiguity in sequencing responsibilities could result in disputes. 
2)  Restricted access windows may create inefficiencies. Owner discretion in defining access periods could introduce unplanned delays. Potential disputes over what constitutes “unreasonable interference.”

  - Flow-Down Obligations: 1) Must be flowed down to subcontractors to ensure their work schedules and site access align with overall project sequencing. Vendors delivering equipment/materials must also be notified of restricted zones and delivery schedules. 
2)  Must be passed down to subcontractors working in restricted areas. Material suppliers and delivery personnel must be aligned with restricted access hours.

  - Redline Recommendations: 1) Insert a clear requirement for the Owner to provide reasonable notice of changes to site access restrictions. Define specific remedies if Owner-caused access restrictions materially impact the Contractor’s performance. Add language ensuring Contractor is entitled to equitable adjustment for delays caused by Owner’s coordination failures. 
2)    Replace vague standard “unreasonably interfere” with an objective performance metric.   Require the Owner to provide at least 48 hours’ notice for changes to restricted access schedules.   Include language entitling Contractor to schedule extensions and/or compensation if restrictions materially impact performance.

  - Harmful Language / Policy Conflicts: 1) The clause shifts coordination risk disproportionately to the Contractor without acknowledging Owner’s responsibility. No compensation mechanism for delays caused by restricted access or Owner interference, which conflicts with fair allocation of risk. 
2)  Current drafting allows unilateral Owner control over access, creating risk of uncompensated delay. Lack of objective standard for “unreasonable interference” exposes Contractor to subjective enforcement.

- Deliverables, Digital Submissions & Documentation Standards

  - Clause Language: 1) “All project deliverables, including drawings, reports, and specifications, shall be submitted in both hard copy and digital formats. Digital submissions must conform to the Owner’s prescribed file format standards and be uploaded through the designated project management platform.”
2) “The Contractor shall provide a final project documentation package, including as-built drawings, test results, certifications, warranties, and operating manuals, in electronic format no later than thirty (30) days after Substantial Completion.”
3) “All submittals shall be provided electronically in PDF format unless otherwise approved. CAD files must be delivered in native format upon request by the Owner.”
4) “The Contractor shall maintain a digital record repository of all project correspondence, RFIs, approved submittals, change directives, and meeting minutes. Upon Final Completion, this repository shall be transferred to the Owner in an organized and indexed electronic format.”

  - Clause Summary: 1) The clause requires that all project deliverables be submitted in both physical and digital formats, with digital submissions adhering to specified file formats and delivery systems.
2) This clause requires submission of comprehensive project documentation, including as-builts and warranties, in electronic form within 30 days of Substantial Completion.
3) The clause mandates electronic submittals in PDF format, with CAD source files available on demand.
4) The clause requires the Contractor to maintain and ultimately deliver a comprehensive digital repository of all project records, including submittals, RFIs, directives, and meeting documentation.

  - Risk Triggers Identified: 1) Ambiguity if the Owner later changes required formats/platforms mid-project. Potential for rejection of deliverables if format requirements are not strictly met. Extra costs if reformatting or resubmissions are required. 
2) Tight timeline (30 days) may be difficult to meet if as-builts or certifications are delayed. Owner may withhold payment until documentation is complete. 
3) Owner gaining full rights to editable CAD files may expose Contractor’s proprietary data. No safeguards for Contractor’s intellectual property. 
4) High administrative burden of maintaining a full indexed repository. Potential Owner claims if the repository is incomplete or not properly organized. Contractor assumes risk of long-term digital storage and data management until project closeout.

  - Flow-Down Obligations: 1) Subcontractors producing deliverables must also comply with digital submission standards.
2) Subcontractors responsible for specific systems (e.g., mechanical/electrical) must provide test results, certifications, and manuals in the required digital format.
3) Subconsultants and subcontractors must prepare and submit documents in both PDF and native file formats as required.
4) Subcontractors and suppliers must provide timely submittals, RFIs, and documentation in digital form to allow inclusion in the repository.

  - Redline Recommendations: 1) Add language obligating the Owner to notify the Contractor of any changes in digital platform or format requirements with reasonable advance notice. Clarify acceptable alternative methods in case the designated system is unavailable. 
2) Extend the timeline to 60 days for more practical compliance. Add provision allowing partial submissions where complete documentation is pending. 
3) Clarify intellectual property protections when providing native CAD files. Limit Owner’s rights to use native files only for maintenance and operational purposes, not redistribution or modification without Contractor’s consent. 
4) Limit Contractor’s responsibility to reasonable efforts and exclude liability for missing documents beyond its control. Specify that the Owner provides the indexing standards upfront to avoid disputes. Add a cure period for correcting repository deficiencies before any penalties or withholdings apply.

  - Harmful Language / Policy Conflicts: 1) Mandatory format compliance without allowance for evolving industry standards may create undue burden. Potential conflict with Contractor’s internal IT policies or cybersecurity controls. 
2) Payment risk if Owner conditions final acceptance or retainage release strictly on documentation delivery without flexibility.
3) Exposes Contractor’s proprietary templates and libraries. Conflicts with standard IP protections unless limited appropriately. 
4) Overly broad requirement without exceptions may conflict with internal document retention policies. Risk of disclosure of confidential or proprietary communications if not narrowed to project-related materials.

## IV. Legal Risk & Enforcement

- Indemnification, Defense & Hold Harmless Provisions

  - Clause Language: 1) “The CONTRACTOR shall indemnify, defend, and hold harmless the OWNER, ENGINEER, and their officers, employees, and agents from and against any and all claims, damages, losses, and expenses, including but not limited to attorney’s fees, arising out of or resulting from the performance of the WORK, provided that any such claim is attributable to bodily injury, sickness, disease, or death, or to injury to or destruction of tangible property (other than the WORK itself), including the loss of use resulting therefrom, but only to the extent caused in whole or in part by the negligent acts or omissions of the CONTRACTOR, a Subcontractor, or anyone directly or indirectly employed by them or anyone for whose acts they may be liable, regardless of whether or not such claim is caused in part by a party indemnified hereunder.”
2) The clause requires the Contractor to indemnify, defend, and hold harmless the Owner and its representatives from claims, damages, liabilities, and expenses (including attorney’s fees) arising out of or related to the Contractor’s work, except to the extent caused by the Owner’s sole negligence.

  - Clause Summary: 1) The clause requires the contractor to indemnify, defend, and hold harmless the owner and engineer against third-party claims for personal injury or property damage arising out of the contractor’s work. It explicitly includes coverage for attorney’s fees and applies even if the indemnitees were partially responsible, so long as the contractor or its subcontractors contributed to the cause.
2) This is a broad indemnification clause obligating the Contractor to bear responsibility for third-party claims and litigation costs, including defense obligations, regardless of fault distribution except for sole negligence of the Owner.

  - Risk Triggers Identified: 1) Broad defense obligation requiring contractor to pay legal fees upfront. Indemnification includes attorney’s fees, which can be open-ended. Covers losses arising even if the indemnitee is partially negligent. Contractor liability may extend to acts of subcontractors and agents. No express carve-outs for gross negligence or willful misconduct of the Owner.
2) Broad scope including “defend” and “hold harmless,” which heightens exposure. Extends liability beyond direct negligence of Contractor (e.g., includes acts of subcontractors, employees, suppliers). Duty to cover attorney’s fees and litigation costs without cap. No carve-out for contributory negligence of Owner (only for sole negligence).

  - Flow-Down Obligations: 1) This indemnification requirement must flow down to subcontractors so that the prime contractor can enforce back-to-back indemnity for claims caused by subcontractors. Subcontracts should mirror this clause.
2) Contractor must flow down equivalent indemnification obligations to subcontractors to ensure risk passes downstream and prevent Contractor from being the sole liable party.

  - Redline Recommendations: 1) Narrow indemnification to “claims to the extent caused by the negligence or willful misconduct of the Contractor.” Remove or limit the duty to defend—convert to reimbursement of defense costs after a determination of fault. Exclude indemnification obligations for indemnitee’s negligence, especially sole negligence. Cap attorney’s fees or provide “reasonable attorney’s fees as awarded by a court.” Add explicit carve-outs for Owner’s gross negligence or willful misconduct.
2) Limit indemnification to losses “to the extent caused by” Contractor’s negligence, not broad “arising out of” language. Remove or qualify “defend” obligation to avoid first-dollar defense cost exposure. Add carve-outs for Owner’s contributory negligence, willful misconduct, or design defects. Cap attorney’s fees and costs to reasonable amounts or proportionate fault.

  - Harmful Language / Policy Conflicts: 1) “Defend” obligation + “including attorney’s fees” creates a very broad, first-dollar defense duty inconsistent with industry-standard balanced risk allocation. Coverage “regardless of whether or not such claim is caused in part by a party indemnified” conflicts with many state anti-indemnity statutes. Expands liability beyond contractor’s control, which is commercially unreasonable.
2) “Defend” obligation creates immediate duty before liability determination. “Hold harmless” may be interpreted broadly, conflicting with insurance coverage. Exclusion only for “sole negligence” of Owner is unusually one-sided.

- Duty to Defend vs. Indemnify Scope Clarifications

  - Clause Language: Not present in contract.

  - Clause Summary: No clause clarifying or limiting a duty to defend separate from indemnity obligations exists.

  - Risk Triggers Identified: Courts may imply a defense obligation into broad indemnity language. Contractor exposure to costs of defense for non-indemnifiable claims.

  - Flow-Down Obligations: None identified for defense. Standard indemnity may flow down, but without explicit defense scope.

  - Redline Recommendations: Add explicit clarification: “Contractor shall have no duty to defend Owner; indemnity obligations are limited to losses adjudicated as Contractor’s responsibility.” Alternatively: “Any duty to defend shall be limited proportionately to Contractor’s negligence, as determined by a court.”

  - Harmful Language / Policy Conflicts: The absence of clarity is itself a risk. Risk of expanded liability due to judicial interpretation.

- Limitations of Liability, Damage Caps & Waivers of Consequential Damages

  - Clause Language: 1) “Neither party shall be liable to the other for incidental, indirect, special, or consequential damages, including lost profits, loss of business, or loss of use, even if advised of the possibility of such damages. Contractor’s aggregate liability under this Agreement shall not exceed the total compensation paid under the Contract.”
2) “Contractor shall not be responsible for any damages beyond direct damages proximately caused by its acts or omissions. All implied warranties are disclaimed, and liability shall not exceed $500,000, regardless of cause.”

  - Clause Summary: 1) This clause limits liability by capping damages at the contract value and waives liability for consequential damages (lost profits, business interruption, etc.).
2) This clause narrows liability further, disclaiming implied warranties and imposing an absolute liability cap at $500,000.

  - Risk Triggers Identified: 1) Absolute liability cap (total compensation paid) restricts recovery, potentially leaving the Owner without recourse if damages exceed payments. Broad waiver of consequential damages may exclude important categories like loss of use or revenue, undermining project protections. 
2) Flat monetary cap ($500,000) may be far below the scale of potential project damages. Disclaimer of implied warranties (merchantability, fitness) eliminates statutory protections.

  - Flow-Down Obligations: 1) If subcontractors are bound by this limitation, Owner may not recover damages fully even if subcontractors cause significant harm.
2) If passed through to subcontractors, this shields subs from responsibility beyond minimal direct damages, undercutting Owner’s protection.

  - Redline Recommendations: 1) Modify liability cap to a higher threshold (e.g., 2–3x contract value). Carve out exceptions for gross negligence, willful misconduct, or statutory violations. Remove blanket waiver of consequential damages or at least preserve Owner’s right to recover for loss of use, delay damages, or third-party claims. 
2) Strike the warranty disclaimer; require at least implied warranties of merchantability and fitness for purpose to remain. Increase or remove liability cap. Add exceptions for insurance-covered losses, third-party indemnity, or statutory obligations.

  - Harmful Language / Policy Conflicts: 1) Blanket waiver of consequential damages conflicts with Owner’s standard policy requiring contractors to remain liable for delay, loss of use, and business interruption. Liability cap equal only to contract payments is overly restrictive and not industry-balanced. 
2) Directly conflicts with Owner’s warranty policy. Liability cap could violate statutory minimums or Owner’s procurement standards.

- Insurance Coverage, Additional Insured & Waiver of Subrogation Clauses

  - Clause Language: 1) “The Contractor shall maintain, at its own expense, insurance coverage including Commercial General Liability, Workers’ Compensation, and Automobile Liability. Such insurance shall name the Owner as an additional insured and provide coverage for the full duration of the project. Certificates of insurance shall be submitted to the Owner prior to commencement of Work.”
2) “To the fullest extent permitted by law, the Contractor waives all rights of subrogation against the Owner, its officers, and employees for damages covered by insurance required under this Contract.”
3) “F. Certificate of Insurance for Products and Completed Operations.”

  - Clause Summary: 1) Contractor must purchase and maintain specified insurance types, naming the Owner as an additional insured, with coverage extending through the project duration. Proof of insurance is required before starting work.
2) Contractor’s insurers cannot pursue reimbursement claims against the Owner for losses already covered under required insurance.
3) At closeout, the contractor must provide a Certificate of Insurance covering products and completed operations.

  - Risk Triggers Identified: 1) Contractor’s failure to maintain required coverage. Lapses in policy or insufficient coverage amounts. Owner’s reliance on contractor-supplied certificates instead of direct verification with insurers. 
2) Lack of waiver may expose Owner to insurer subrogation claims. Limited enforceability if state law restricts waivers.
3) Lack of clarity on coverage duration or limits. Potential lapse in coverage during warranty period. No verification mechanism of insurance validity.

  - Flow-Down Obligations: 1) Subcontractors may also be required to carry comparable coverage and name both the Contractor and Owner as additional insureds.
2) Subcontractors’ policies should also include waivers of subrogation in favor of Contractor and Owner.
3) Implied flow-down if subcontractors provide such products or services—should be made explicit.

  - Redline Recommendations: 1) Specify minimum coverage limits (e.g., $2M per occurrence). Require notice of cancellation or material change at least 30 days prior. Add requirement for primary and non-contributory coverage language. Clarify that insurance must be placed with A-rated carriers. 
2) Ensure waiver applies to all tiers of subcontractors. Confirm waiver language is included on actual policy endorsements (not just contract text).
3) Require naming the Owner as an additional insured. Specify coverage duration post-completion (e.g., 2–3 years). Require submission prior to final payment.

  - Harmful Language / Policy Conflicts: 1) Risk of insufficient coverage if limits are undefined. Absence of explicit waiver of subrogation language may allow insurer recourse against Owner. 
2) Without this waiver, Owner could face indirect liability despite insurance coverage.
3) Clause is vague; without further detail, it risks underinsurance or post-completion exposure.

- Dispute Resolution (Mediation, Arbitration, Litigation)

  - Clause Language: 1) “All claims, disputes, and other matters in question arising out of or relating to this Contract shall be submitted first to non-binding mediation administered under the Construction Industry Mediation Rules. If mediation fails to resolve the dispute, the matter shall be referred to binding arbitration pursuant to the rules of the American Arbitration Association, and judgment on the award rendered by the arbitrator(s) may be entered in any court having jurisdiction.”
2) “In the event of any dispute not resolved by negotiation between the Parties within thirty (30) days, either Party may initiate litigation in a court of competent jurisdiction located in the State of Florida. Nothing herein shall preclude the Parties from agreeing to mediate prior to litigation.”

  - Clause Summary: 1) This clause mandates a tiered dispute resolution process: mediation first, then binding arbitration if mediation is unsuccessful, with enforcement of arbitral awards in court.
2) This clause allows disputes to be taken directly to litigation after a 30-day negotiation period, while preserving an option for voluntary mediation.

  - Risk Triggers Identified: 1) Mandatory arbitration limits access to litigation and jury trial. No explicit carve-outs for urgent injunctive relief. Silence on cost allocation could lead to disproportionate burdens. 
2) Exposure to full litigation costs and delays. Lack of mandatory mediation may escalate disputes prematurely. Forum selection locked to Florida, limiting flexibility.

  - Flow-Down Obligations: 1) Subcontracts must incorporate the same mediation-arbitration sequence to avoid conflicting dispute resolution forums.
2) Subcontracts must adopt same dispute forum to avoid fragmentation and parallel disputes in multiple venues.

  - Redline Recommendations: 1) Insert language reserving the right to pursue injunctive relief in court. Specify cost-sharing of mediation and arbitration fees. Allow contractor option to consolidate disputes with subcontractors. 
2) Require mediation as a mandatory precondition before litigation. Add arbitration option for certain technical disputes where speed is critical. Clarify venue clause to allow flexibility or neutrality.

  - Harmful Language / Policy Conflicts: 1) Waiver of litigation rights may conflict with internal policy requiring at least one forum for judicial resolution. Risk of excessive arbitration costs without cost allocation limits. 
2) Conflict with corporate ADR-first policy if mediation is not mandated. Potential inconsistency if subcontractors adopt arbitration instead of litigation.

- Flow-Down Clauses (Prime-to-Subcontract Risk Pass-Through)

  - Clause Language: 1) “Subcontractor agrees to be bound to Contractor by the terms of the Prime Contract and to assume toward Contractor all of the obligations and responsibilities that Contractor assumes toward Owner, to the extent applicable to the Work provided under this Subcontract.”
2) “In the event of a conflict between the provisions of this Subcontract and the Prime Contract, the more stringent requirement shall apply to Subcontractor.”

  - Clause Summary: 1) This clause requires the subcontractor to adopt all obligations from the prime contract and pass them down, effectively mirroring the prime contractor’s commitments to the owner.
2) This clause creates a hierarchy between the subcontract and prime contract, imposing whichever obligation is stricter.

  - Risk Triggers Identified: 1) Broad “to the extent applicable” language risks imposing owner-level obligations beyond subcontractor’s scope. Lack of carve-outs for obligations unique to prime contractor (e.g., insurance levels, indemnities). 
2) Elevates subcontractor’s risk exposure by defaulting to “more stringent” obligations. Can cause operational confusion and conflicting interpretations of responsibility.

  - Flow-Down Obligations: 1) All owner–contractor obligations are pushed downstream to the subcontractor, unless explicitly excluded. Includes compliance with specifications, performance standards, and possibly administrative burdens. 
2) Subcontractor automatically absorbs the stricter standard, even if not negotiated. May inadvertently extend liability beyond subcontractor’s anticipated role.

  - Redline Recommendations: 1) Narrow flow-down obligations to only those “directly related to the Work performed by Subcontractor.” Exclude prime-specific obligations such as general indemnities, liquidated damages, and insurance coverages. Add clarification that subcontractor is not responsible for obligations outside its scope or control. 
2) Replace with clear precedence rules (e.g., subcontract terms govern unless specifically incorporated from prime). Limit application of prime contract provisions to those explicitly referenced.

  - Harmful Language / Policy Conflicts: 1) Risk of subcontractor assuming disproportionate liability. May conflict with internal policy restricting downstream risk pass-through without limits. 
2) Risk of unfair expansion of subcontractor duties. May violate policy requiring subcontractor exposure to be limited to scope-defined risks.

- Subcontracting Restrictions, Approval & Substitution Requirements

  - Clause Language: 1) “The OWNER may require the CONTRACTOR to furnish at the CONTRACTOR's expense a special performance guarantee or other surety with respect to any substitute. Acceptance by the ENGINEER of a substitute item proposed by the CONTRACTOR shall not relieve the CONTRACTOR of the responsibility for full compliance with the Contract Documents and for adequacy of the substitute item. The CONTRACTOR shall be responsible for resultant changes and all additional costs which the accepted substitution requires in the CONTRACTOR WORK, the WORK of its Subcontractors and of other Contractors, and shall effect such changes without cost to the OWNER.”
2) “Substitutions will not be considered when indicated on shop drawings or product data submittals without separate formal request, when requested directly by Subcontractor or supplier, or when acceptance will require substantial revision of Contract Documents. Substitute products shall not be ordered or installed without written acceptance. Only one request for substitution for each product will be considered.”
3) “A request for a substitution constitutes a representation that CONTRACTOR has investigated the proposed product and determined that it is equal to or superior in all respects to that specified, will provide the same guarantees or bonds, will coordinate the installation of an accepted substitution into the WORK, and waives all claims for additional costs which may subsequently become apparent.”

  - Clause Summary: 1) This provision establishes restrictions and obligations tied to substitutions or replacements by subcontractors. Approval does not absolve the contractor of liability, and the contractor bears all associated costs for substitution impacts.
2) Limits substitution requests by requiring formal submission, OWNER/ENGINEER written acceptance, and restricting subcontractor-initiated requests.
3) Imposes strict requirements on substitution requests, making contractor warranties equal to specified products and waiving claims for later cost recovery.

  - Risk Triggers Identified: 1) Subcontractor substitution without adequate vetting. Owner requiring additional surety for substitutes. Risk of contractor absorbing additional costs from subcontractor substitutions. 
2) Subcontractors attempting informal substitutions. Delay risk due to formal approval process. Cost impact if substitutions are rejected after request.
3)    Contractor assumes performance liability equal to original specified product.   Waiver of claims prevents cost recovery for unforeseen substitution impacts.

  - Flow-Down Obligations: 1) Subcontractors must ensure compliance with substitution requirements and assume responsibility for impacts on schedule, cost, and compliance with project specifications.
2) Subcontractors must submit formal substitution requests via the contractor and comply with OWNER/ENGINEER review processes.
3) Subcontractors must back guarantees and coordinate substitution-related changes without cost recovery.

  - Redline Recommendations: 1) Clarify that OWNER approval of substitutions does not unreasonably withhold consent. Define “additional costs” explicitly to avoid broad contractor liability. Limit OWNER’s right to demand special surety only where justified. 
2) Allow multiple substitution requests when justified. Clarify turnaround time for OWNER/ENGINEER decisions. Permit subcontractor-originated requests if routed through contractor.
3) Strike waiver of claims for unforeseeable costs. Limit representation to “reasonable equivalence” rather than “equal or superior in all respects.”

  - Harmful Language / Policy Conflicts: 1) Broad contractor liability for all substitution impacts may create unfair financial burdens. Lack of an objective standard for OWNER’s requirement of special performance guarantees. 
2) One-request limit may force contractors into uneconomical product choices. Ambiguity around “substantial revision” gives OWNER excessive discretion.
3) Waiver clause conflicts with fair cost allocation principles. Unqualified “equal or superior” standard sets unreasonably high liability.

- Background Screening, Security Clearance & Worker Eligibility Requirements

  - Clause Language: 1) “All applicants for employment are subject to submitting to pre-hire drug testing once a conditional offer of employment has been made. To the extent permitted by law, the Company may condition employment offers on the successful completion and passing of a drug screening administered by the Company or a Florida licensed independent testing facility of the Company’s choice.”
2) “This employer participates in E-Verify and will provide the federal government with your Form I-9 information to confirm that you are authorized to work in the U.S. Employers can only use E-Verify once you have accepted a job offer and completed the Form I-9.”
3) “In accordance with applicable Florida law, the Company may subject employees who violate the Company’s safety or security procedures or who are in work-related accidents to drug and alcohol testing. No injuries or property damage are necessary to require drug testing.”
4) “This employer is required to give you written instructions and an opportunity to contact DHS or SSA so you can begin to resolve the issue before the employer can take any action against you, including terminating your employment.”
5) “All persons offered employment with the Company are required to undergo a pre-employment background check, which may include criminal, civil and driver’s license check, and drug screening as a condition of employment and continued employment. Other screening may be required as determined by the Company during employment.”
6) “Each new team member must complete a Form I-9. The completed I-9 form must be provided within 3 business days of your start date. Any employee authorized to work under a temporary protected status or other exemption must provide an updated letter to the Human Resources Department prior to the expiration of the current authorization.”
7) “Testing will be performed and is implemented pursuant to Florida Statute §440.101 & §440.102 and Chapter 59A-24 Drug-Free Workplace Standards, including Job Applicant, Reasonable Suspicion, Routine Fitness for Duty, and Follow-up Drug Testing.”

  - Clause Summary: 1) Employment offers are conditional on applicants passing a drug test. This ensures compliance with workplace safety and substance-free policies.
2) Employer mandates compliance with federal E-Verify system to confirm employee eligibility to work.
3) Post-incident and safety/security violation drug testing may be required, even absent property damage or injury.
4) Ensures due process for employees flagged by E-Verify before termination action is taken.
5) This clause mandates pre-employment background checks, including criminal, civil, and driver’s license checks, plus drug screening. It also reserves the Company’s right to impose further screening during employment.
6) This clause enforces compliance with federal immigration laws by requiring timely completion of Form I-9 and updated documentation for employees working under temporary authorization.
7) This clause establishes drug testing requirements consistent with Florida’s Drug-Free Workplace laws, covering pre-employment, reasonable suspicion, fitness-for-duty, and follow-up testing.

  - Risk Triggers Identified: 1) Candidate refusal or failure of drug test delaying staffing. Legal exposure if drug testing not applied consistently. Risk of wrongful termination/discrimination claims.
2) Delays in DHS/SSA responses could stall onboarding. Potential wrongful termination if eligibility disputes are not resolved timely. 
3) Disputes regarding cause and justification for testing. Potential wrongful termination litigation. 
4) Failure to provide instructions or opportunity could breach compliance. Administrative delays affecting project staffing.
5) Potential delays in onboarding due to background screening process. Risk of inconsistent screening application across employees. Exposure to privacy claims if screenings are not conducted lawfully. 
6) Non-compliance could lead to federal penalties or fines. Risk of project delays if work authorization lapses.
7) Employee refusal or failure of drug test resulting in disqualification. Administrative burdens tied to ongoing compliance and documentation. Possible disputes regarding testing fairness or procedures.

  - Flow-Down Obligations: 1) Subcontractors must enforce equivalent pre-employment drug testing for site staff.
2) Subcontractors must also utilize E-Verify for their hires if they provide labor on the project.
3) Subcontractors must ensure workers comply with post-incident testing requirements.
4) Subcontractors must also provide workers due process if eligibility questions arise.
5) Subcontractors must comply with the same background screening and drug-testing requirements to ensure workforce eligibility and compliance with company policy.
6) Subcontractors must ensure their employees also comply with I-9 verification and immigration law requirements.
7) Subcontractors must implement equivalent drug testing standards for their workforce.

  - Redline Recommendations: 1) Specify uniform application of testing to avoid discrimination. Require alignment with federal and state law testing procedures.
2) Include procedure for handling tentative non-confirmations fairly. Specify a time frame for employee resolution efforts. 
3) Require objective criteria to trigger testing. Include protections for prescription drug use disclosure. 
4) Add maximum resolution period to avoid indefinite delays. Require written documentation of compliance with DHS/SSA steps. 
5) Define scope and limits of “other screening” to avoid arbitrary requirements. Establish timelines for completing checks to minimize project delays. Clarify compliance with applicable federal and state privacy laws (e.g., FCRA). 
6) Require clear documentation retention and audit procedures. Specify consequences for late or missing submissions to avoid liability. 
7) Include confidentiality safeguards for test results. Define appeal or retesting process for contested results. Clarify alignment with federal DOT requirements if applicable.

  - Harmful Language / Policy Conflicts: 1) Ambiguity in “Company’s choice” of facility may lead to disputes over impartiality. Absence of rehabilitation or retesting provisions could create unnecessary turnover. 
2) Risk of discriminatory application if E-Verify inconsistently enforced. Exposure to claims under 8 U.S.C. § 1324b if national origin or citizenship status impacts hiring. 
3) Overly broad scope could conflict with employee rights. Lack of specific standards may be challenged as arbitrary. 
4) Ambiguity about “opportunity” may allow for inconsistent application. Prolonged disputes could disrupt staffing timelines.
5) “Other screening” is overly broad and grants excessive discretion to employer. Risk of conflict with privacy and equal employment laws if not narrowly defined. 
6) No provisions for accommodating delays outside employee’s control (e.g., USCIS processing). Lack of explicit employer responsibility for ensuring timely follow-up on temporary status renewals. 
7) Broad employer discretion may expose company to discrimination or wrongful termination claims. Lacks explicit employee rights protections regarding medical prescriptions.

- Safety Standards, OSHA Compliance & Site-Specific Safety Obligations

  - Clause Language: 1) “The CONTRACTOR shall maintain trench safety and comply with current OSHA regulations and the Trench Safety Act. The CONTRACTOR shall maintain and keep all safety barricades, signage, flashers, and detours, in operating condition. A copy of the approved MOT plans, and details, shall be on site at all times.”
2) “The contractor is responsible for designing and constructing stable, temporary excavations and should shore, slope or bench the sides of the excavations as required, to maintain stability of both the excavation sides and bottom. All excavations should comply with applicable local, state and federal safety regulations, including the current OSHA Excavation and Trench Safety Standards.”
3) “As a minimum, all temporary excavations should be sloped or braced as required by Occupational Health and Safety Administration (OSHA) regulations to provide stability and safe working conditions… shoring and shielding procedures should conform to those presented in OSHA standards.”
4) “In the event a trench must be left open after hours, it shall be done so only with the express written permission… CONTRACTOR shall maintain trench safety and comply with current OSHA regulations and the Trench Safety Act.”
5) “The contractor is responsible for designing and constructing stable, temporary excavations and should shore, slope or bench the sides of the excavations as required… All excavations should comply with applicable local, state and federal safety regulations, including the current OSHA Excavation and Trench Safety Standards.”
6) “It is mandated by this federal regulation that all excavations, whether they be utility trenches, basement excavations, or footing excavations, be constructed in accordance with the new OSHA guidelines… A competent person should evaluate the excavations for stability prior to entry by personnel.”

  - Clause Summary: 1) Requires the contractor to comply with OSHA trench safety regulations and the Trench Safety Act, ensuring all safety devices (barricades, signage, flashers) are maintained. MOT (Maintenance of Traffic) plans must be available onsite at all times.
2) Mandates compliance with OSHA excavation and trench safety standards, requiring safe construction and stabilization of temporary excavations.
3) Contractor must ensure all temporary excavations comply with OSHA excavation and trenching standards, including slope, bracing, shoring, or shielding.
4) Trenches left open after working hours require special approval and must comply with OSHA trench safety and Trench Safety Act requirements.
5) Contractor bears full responsibility for excavation stability, with mandatory compliance to OSHA and FDOT standards.
6) OSHA’s 29 CFR Part 1926 Subpart P applies to all excavation work. Contractor must provide shoring, bracing, trench boxes, or sloping as needed, with a competent person inspecting stability before entry.

  - Risk Triggers Identified: 1) OSHA violations (trench collapses, inadequate protection). Failure to maintain required safety devices or provide approved MOT plans. Regulatory fines, work stoppages, and liability for worker/public injuries. 
2) Collapse or cave-in due to improper shoring/slope design. OSHA citations and penalties for noncompliance. Exposure to third-party liability claims for accidents. 
3) Failure to slope or brace trenches. Unsupported cuts near utilities/structures. Excavation deeper than safe limits without proper support. 
4) Leaving trenches unsecured after hours. Lack of protective barricades, signage, or security. 
5) Inadequate shoring or sloping. Excavation collapse causing injury or property damage. 
6) Entry into uninspected or unstable excavations. Failure to employ competent person for trench safety.

  - Flow-Down Obligations: 1) Must be passed to subcontractors engaged in excavation or site work to ensure full compliance with trench safety requirements.
2) Subcontractors performing excavation must comply with OSHA standards and follow shoring/sloping requirements.
3) Subcontractors must also comply with OSHA trenching and excavation standards and implement required shoring/sloping.
4) Applies to all subcontractors performing excavation or trench work.
5) Subcontractors performing excavation must follow same OSHA trenching and excavation standards.
6) Subcontractors must also designate competent persons and follow OSHA excavation standards.

  - Redline Recommendations: 1) Specify explicit contractor liability for OSHA fines and penalties. Add requirement for daily safety inspections and documented trench logs. Clarify responsibility for subcontractors’ compliance. 
2) Require contractor to submit a trench/excavation safety plan for engineer approval before work begins. Clarify liability for subcontractor violations. Include requirement for independent safety audits for excavation work. 
3) Add explicit requirement that contractor must submit an OSHA compliance plan before commencing excavation.
4) Require trench closure plans for all excavations >5 feet before end of shift, unless emergency permission is granted.
5) Add requirement for a “competent person” inspection per OSHA before workers enter excavation.
6) Make it mandatory that a daily trench log be kept and signed by the competent person.

  - Harmful Language / Policy Conflicts: 1) Broad obligation without clear inspection/enforcement standards may lead to disputes. No limitation on contractor’s liability for third-party noncompliance (e.g., subcontractors). 
2) Lacks reference to specific OSHA sections, leaving compliance interpretation broad. Does not address responsibility for monitoring ongoing excavation safety conditions. 
3) None. The clause aligns with OSHA standards.
4) Potential gap: no explicit reference to penalties or stop-work authority if contractor violates trench safety.
5) Ambiguity in “should shore, slope or bench” – should be replaced with “shall” for enforceability.
6) No conflicts – this clause strengthens compliance obligations.

- Site Conditions, Differing Site Conditions & Changed Circumstances Clauses

  - Clause Language: 1) “The subsurface investigation for conditions of the project site is the sole responsibility of the CONTRACTOR. In preparing the Bid, the CONTRACTOR shall make all subsurface or surface investigations necessary to provide proper background and knowledge to determine the nature and extent of WORK required. OWNER or ENGINEER will provide minimal subsurface information upon request, and makes no warranties or guarantees concerning the nature of materials to be encountered on the site.”
2) “The CONTRACTOR shall be solely responsible for all excavating to complete the Contract. No extra payment will be allowed for type or classification of material in excavation. The CONTRACTOR shall satisfy by site inspection, borings, probings, etc., prior to bidding, as to the subsurface character of the material.”
3) “Conditions that occur on the site that cause the system to be modified, shall be presented as shop drawings by the CONTRACTOR and approved by the ENGINEER, prior to construction. The existence and location of utilities shall be thoroughly investigated and verified by the CONTRACTOR before the WORK begins. Should obstructions be encountered which interfere with the WORK, the ENGINEER shall be consulted for relocation. The CONTRACTOR shall be responsible for the immediate repair of any damage to utilities caused by the WORK.”

  - Clause Summary: 1) The contractor assumes full responsibility for investigating and understanding site and subsurface conditions. The owner and engineer expressly disclaim warranties or guarantees for site conditions.
2) Contractor is responsible for excavation regardless of subsurface material encountered and cannot claim extra payment for material classification. Contractor must self-verify conditions prior to bid.
3) Contractor must identify site conditions or obstructions requiring design modifications, secure approval for changes, and bear responsibility for utility investigation and damage repair.

  - Risk Triggers Identified: 1) Contractor bears risk of unforeseen soil or subsurface conditions. Potential for unexpected excavation costs due to lack of reliable subsurface information. No owner liability for inaccuracies in subsurface data provided. 
2) Discovery of rock, unstable soils, or other difficult materials without compensation. Cost overruns tied to site conditions unknown at time of bid. Strict allocation of risk to contractor. 
3) Unforeseen utilities or obstructions requiring redesign. Contractor liability for damage to undisclosed or unmapped utilities. Project delays from required redesign and approvals.

  - Flow-Down Obligations: 1) Subcontractors performing excavation or site-related work must assume responsibility for site condition verification and cannot rely on owner-provided information.
2) Subcontractors conducting excavation must bear same risks without entitlement to additional compensation for unexpected conditions.
3) Subcontractors must survey site conditions, account for existing utilities, and assume liability for damages to utilities.

  - Redline Recommendations: 1) Require owner to disclose all known subsurface reports and investigations. Include a differing site conditions clause to allow equitable adjustment for unforeseen conditions. Narrow disclaimer to exclude conditions reasonably foreseeable from provided information.
2) Insert clause granting adjustments for materially differing or unforeseen conditions. Limit contractor’s responsibility to conditions reasonably discoverable by standard investigation. Require owner to provide baseline geotechnical data. 
3) Shift risk of undisclosed utilities to owner, at least where records are incomplete. Provide cost-sharing mechanism for major redesigns caused by unforeseen conditions. Require owner to supply all available utility mapping.

  - Harmful Language / Policy Conflicts: 1) Complete disclaimer of owner responsibility conflicts with industry norms (e.g., Federal “Differing Site Conditions” clauses). Shifts disproportionate financial burden and risk of latent conditions entirely onto contractor. 
2) Absolute denial of compensation for unforeseen conditions undermines equitable risk allocation. Conflicts with federal and many state public contract norms requiring relief for latent conditions. 
3) Unqualified contractor liability for all utility damage imposes undue risk where utility records may be incomplete. No relief mechanism for changed site conditions requiring redesign.

- Environmental Hazards, Waste Disposal & Hazardous Materials Provisions

  - Clause Language: 1) “The CONTRACTOR shall construct and use a separate storage area for hazardous materials used in constructing the WORK. For the purpose of this paragraph, hazardous materials to be stored in the separate area are all products labeled with any of the following terms: Warning, Caution, Poisonous, Toxic, Flammable, Corrosive, Reactive, or Explosive. In addition, whether or not so labeled, the following materials shall be stored in the separate area: diesel fuel, gasoline, new and used motor oil, hydraulic fluid, cement, paints and paint thinners, two-part epoxy coatings, sealants, asphaltic products, glues, solvents, wood preservatives, sand blast materials, and spill absorbent. Hazardous materials shall be stored in groupings according to the Material Safety Data Sheets. The CONTRACTOR shall develop and submit to the ENGINEER a plan for storing and disposing of the materials above. The CONTRACTOR shall obtain and submit to the ENGINEER a single EPA number for wastes generated at the site. The separate storage area shall meet all the requirements of all authorities having jurisdiction over the storage of hazardous materials. All hazardous materials which are delivered in containers shall be stored in the original containers until use. Hazardous materials which are delivered in bulk shall be stored in containers which meet the requirements of authorities having jurisdiction.”
2) “Conduct cleaning and disposal operations to comply with codes, ordinances, regulations, and anti-pollution laws… Provide on-site containers for the collection of waste materials, debris, and rubbish. Remove waste materials, debris and rubbish from the site periodically and dispose of at legal disposal areas away from the site.”
3) “Demolition operations must use water sprinkling, temporary enclosures, and other suitable methods to limit dust and dirt rising and scattering into the air to the lowest practical level. Comply with governing regulations pertaining to environmental protection. Clean adjacent structures and improvements of dust, dirt, and debris caused by demolition operations as directed by the CITY or ENGINEER or governing authorities. Material resulting from demolition and not scheduled for salvaging shall become the property of the CONTRACTOR and shall be removed from site and legally disposed of off-site on a daily basis unless otherwise directed by the ENGINEER.”
4) “The use and disposal of hazardous substances has attracted much attention in recent years due to increased awareness of protecting the environment in which we live. … Most petroleum-based solvents, cleaners, and oils cannot be disposed in water systems or ordinary landfills. If you have waste oils, solvents, or cleaners on your job site, make sure that you check the SDS for proper disposal methods prior to discarding the material. Do not release any material into drains, storm sewers, or onto the ground unless it has been cleared by your supervisor. Contain oils or solvents by means of catch pans and/or floor dry materials. Repair and maintain equipment to avoid oil and solvent leaks.”
5) “The CONTRACTOR is responsible that all WORK … shall comply with all EPA, OSHA, RCRA, NFPA, and any other Federal, State, and Local Regulations governing the storage and conveyance of hazardous materials, including petroleum products. Where no specific regulations exist, all chemical, hazardous, and petroleum product piping and storage in underground locations must be installed with double containment piping and tanks, or in separate concrete trenches and vaults, or with an approved lining which cannot be penetrated by the chemicals, unless waived in writing by the OWNER.”

  - Clause Summary: 1) This clause mandates safe storage, handling, and disposal of hazardous materials. It requires contractors to submit a waste management plan, obtain an EPA number for site waste, and comply with authority requirements. Materials must be stored in designated areas with segregation by type.
2) This provision sets requirements for proper waste disposal, compliance with environmental regulations, and safe removal of construction debris from the site.
3) This clause addresses environmental protections during demolition, requiring dust control, cleanup of affected areas, and proper off-site legal disposal of demolition debris.
4) This clause sets forth environmental controls for the handling, containment, and disposal of hazardous materials (oils, solvents, cleaners) to prevent pollution of soil and water systems.
5) This clause establishes broad contractor responsibility for compliance with hazardous material regulations and mandates protective design standards for underground storage and conveyance.

  - Risk Triggers Identified: 1) Failure to develop or submit a compliant hazardous waste plan. Improper segregation of hazardous materials. Lack of EPA compliance for waste disposal. Spillage or mishandling of bulk hazardous substances. 
2) Improper waste segregation leading to regulatory violations. Disposal at non-permitted facilities. Accumulation of waste materials creating site hazards. 
3) Inadequate dust control measures creating OSHA or EPA violations. Improper disposal of demolition debris. Daily off-site disposal requirement creating cost and scheduling pressure. 
4) Improper disposal of solvents, oils, or cleaners. Release of hazardous materials into drains, storm sewers, or onto soil. Equipment leaks leading to contamination. 
5) Non-compliance with EPA, OSHA, RCRA, NFPA regulations. Use of single-containment systems in underground storage. Reliance on owner waivers to reduce environmental safeguards.

  - Flow-Down Obligations: 1) Subcontractors handling or generating hazardous waste must follow the contractor’s hazardous materials storage/disposal plan and comply with regulatory requirements.
2) Subcontractors must collect and dispose of waste materials in accordance with project-wide protocols and legal standards.
3) Subcontractors conducting demolition must comply with dust suppression and lawful disposal requirements, including off-site daily removal.
4) Contractors must instruct and monitor employees on disposal practices and containment. Subcontractors handling hazardous substances must comply with SDS and environmental control requirements.
5) All subcontractors involved in storage, handling, or conveyance of hazardous materials must comply with federal/state/local regulations and double-containment requirements.

  - Redline Recommendations: 1) Specify timelines for submission of hazardous materials management plans. Require OWNER review/approval of EPA number documentation before work begins. Include liability allocation for spills caused by OWNER-directed changes in material use. 
2) Require certification from disposal facilities confirming lawful handling of waste. Add penalties for non-compliance with waste management requirements. 
3) Clarify responsibility for disposal costs when OWNER orders daily removal beyond normal operations. Require OWNER approval of disposal sites to ensure regulatory compliance. 
4) Insert explicit penalties/liquidated damages for non-compliance with disposal requirements. Require reporting and documentation of hazardous waste disposal. Add reference to EPA/RCRA regulations to strengthen compliance enforceability. 
5) Remove or tighten “unless waived in writing by the OWNER” to prevent unsafe environmental practices. Add requirement for independent environmental compliance audits. Clarify that waivers cannot supersede regulatory requirements.

  - Harmful Language / Policy Conflicts: 1) Contractor bears full liability without clear limit for hazardous materials compliance. No explicit requirement for OWNER to provide information about pre-existing site contamination. 
2) Ambiguity around “periodically” could result in inconsistent enforcement. No allocation of liability for OWNER-directed waste handling methods that may breach environmental standards. 
3) Shifts all disposal obligations and liabilities onto CONTRACTOR without limit. Daily removal mandate may be operationally impractical without flexibility for volume spikes. 
4) Clause lacks specificity on “approval by supervisor” and should tie clearance to regulatory compliance, not discretionary approval. Does not explicitly require third-party licensed hazardous waste disposal firms, which may conflict with stricter owner or regulatory policies. 
5) “Waived in writing by the OWNER” undermines compliance obligations. Absence of clear enforcement/penalty language for violations may conflict with owner’s zero-tolerance environmental policy.

- Conflicting Documents / Order of Precedence Clauses

  - Clause Language: “Except as noted, all materials and quality of work shall meet the requirements of the latest editions of the following publications: [list of standards]. In the event of conflict between the Contract Documents, the order of precedence shall be: (1) Change Orders and other modifications, (2) Addenda, (3) Specifications, (4) Drawings.”

  - Clause Summary: This clause establishes an order of precedence hierarchy among contract documents (change orders, addenda, specifications, and drawings) in the event of conflicting requirements. It ensures there is a default resolution mechanism when discrepancies exist.

  - Risk Triggers Identified: Ambiguities between drawings and specifications may lead to disputes. Overreliance on a rigid hierarchy could unfairly shift responsibility for coordination to the contractor. Absence of language covering conflicts with incorporated external standards or regulations.

  - Flow-Down Obligations: Subcontractors must be aware of and comply with the hierarchy of documents. Prime contractor must ensure subs and suppliers follow specifications and prioritize directives consistent with this clause.

  - Redline Recommendations: Add language clarifying that Owner bears responsibility for consistency of documents and that Contractor is entitled to rely on drawings and specifications as coordinated. Insert provision that more stringent requirement shall apply when multiple standards are referenced, unless otherwise directed in writing. Add express inclusion of regulatory codes and laws at the top of the hierarchy to avoid compliance conflicts.

  - Harmful Language / Policy Conflicts: The hierarchy as written favors Owner-issued documents without ensuring Contractor protection for inconsistencies. No explicit safeguard for cost/time impacts arising from conflicts—may expose Contractor to uncompensated risk. Absence of reference to industry standard order-of-precedence models (e.g., EJCDC, AIA) could limit fairness.

- Setoff & Withholding Rights (Owner’s Right to Deduct or Withhold Payment)

  - Clause Language: 1) “OWNER will deduct the amount of such compensation from the final payment to the CONTRACTOR.”
2) “Statement shall reflect all adjustments to the Contract Sum: … d. Deductions for uncorrected WORK. e. Penalties and Bonuses. f. Deductions for liquidated damages. g. Deductions for reinspection payments.”
3) “Statement shall reflect all adjustments to the Contract Sum: … d. Deductions for uncorrected WORK. e. Penalties and Bonuses. f. Deductions for liquidated damages. g. Deductions for reinspection payments. h. Other adjustments.”
4) “Should OWNER or ENGINEER perform re-inspections due to failure of the WORK to comply with the claims of status of completion made by the CONTRACTOR: 1. CONTRACTOR will compensate OWNER or ENGINEER for such additional services, and/or 2. OWNER will deduct the amount of such compensation from the final payment to the CONTRACTOR.”
5) “Additions and deductions resulting from: … Deductions for uncorrected WORK … Deductions for liquidated damages … Deductions for reinspection payments … Other adjustments … Sum remaining due.”

  - Clause Summary: 1) The Owner retains the right to deduct reinspection costs from the Contractor’s final payment if reinspection is required due to the Contractor’s failure to complete work properly.
2) This provision mandates that the Contractor’s final accounting must include deductions for uncorrected work, liquidated damages, penalties, and reinspection costs, reinforcing the Owner’s right to withhold payments.
3) The Owner reserves the right to adjust the final Contract Sum by deducting amounts for uncorrected work, penalties, liquidated damages, reinspection costs, and other specified adjustments before final payment is issued.
4) The Owner may deduct the costs of re-inspections directly from the Contractor’s payment if the Contractor falsely claims work is complete or if the work fails to meet contract standards.
5) At final payment stage, the Owner has explicit authority to deduct sums for uncorrected work, damages, and other categories before certifying the final balance due.

  - Risk Triggers Identified: 1) Work declared incomplete or defective. Reinspection by Owner/Engineer due to Contractor fault. 
2) Failure to correct defective work. Project delays triggering liquidated damages. Multiple reinspections required. 
3) Failure to correct defective or incomplete work. Delays that trigger liquidated damages. Reinspection requirements due to Contractor noncompliance. Owner’s discretionary deductions for penalties and other adjustments.
4) Contractor misrepresentation of completion status. Substandard work requiring repeat inspections. Owner’s unilateral assessment of costs. 
5) Completion with unresolved defects. Triggering of liquidated damages due to delay. Disputes over “other adjustments” that may be broad in scope.

  - Flow-Down Obligations: 1) This clause may need to be flowed down to subcontractors, ensuring they understand that defective work or failed inspections at their level may result in deductions.
2) Should be flowed down to subcontractors to ensure subcontractor-caused defects, delays, or nonconformance can be deducted and passed through.
3) If subcontractors perform defective or incomplete work, the prime contractor must cascade this risk to subcontractors, ensuring that they bear responsibility for rework or deductions attributable to their performance.
4) Contractor must pass this obligation down to subcontractors, ensuring they bear costs of reinspection if deficiencies are attributable to their work.
5) Prime contractor should obligate subs to indemnify for sums deducted due to their deficiencies, delays, or reinspection failures.

  - Redline Recommendations: 1) Clarify that deductions will only apply to reasonable, documented reinspection costs. Add a contractor right to contest deductions through a dispute resolution mechanism. 
2) Limit deductions to specific, objectively measurable categories (not broad “other adjustments”). Require written notice to Contractor before deductions are applied. 
3) Narrow “other adjustments” to a defined list to prevent open-ended deductions. Require mutual agreement or independent verification before deductions are applied. Cap reinspection costs or require advance notice before charging deductions. 
4) Add requirement that reinspection costs be “reasonable and documented.” Limit deductions to direct inspection costs, excluding overhead. Insert notice and opportunity to cure before deductions occur.
5) Define “uncorrected WORK” as “defective work unremedied after notice and cure opportunity.” Exclude Owner’s consequential costs unless specifically tied to direct damages. Require reconciliation and documentation for all deductions.

  - Harmful Language / Policy Conflicts: 1) Uncapped deduction authority could expose the Contractor to significant financial withholding beyond proportionate damages.
2) Limit deductions to specific, objectively measurable categories (not broad “other adjustments”). Require written notice to Contractor before deductions are applied. 
3) “Other adjustments” is vague and could enable arbitrary withholding. No requirement that deductions be proportional to the damage caused. Contractor bears unilateral exposure without reciprocal rights against the Owner. 
4) Owner’s right to deduct without prior verification process is unfavorable. No proportionality safeguard—minor deficiencies could trigger excessive deductions. 
5) Owner discretion creates risk of arbitrary or duplicative deductions. Overlaps with damages provisions—risk of double-penalization.

## V. Regulatory & Compliance Terms

- Certified Payroll, Recordkeeping & Reporting Obligations

  - Clause Language: 1) “The Company complies with all applicable federal and state wage and hour laws and regulations. To satisfy these requirements, all non-exempt employees must accurately record their hours worked each day. At the end of each week, the team member and their supervisor must sign the time sheet attesting to its correctness before forwarding it to the Company Payroll Department. The Company prohibits all non-exempt employees from performing any work without recording their time for payroll purposes (i.e., ‘working off the clock’). No one at the Company is authorized to work off the clock and no one at the Company has the authority to require any employee to perform off-the-clock work. Employees who engage in fraudulent timekeeping, recording time for others, falsifications of time records, or any other violation of this policy will be subject to disciplinary action, up to and including termination of employment.”
2) “The Company must comply with all court-ordered payroll deductions and garnishments. Fees for processing involuntary deductions will be charged as allowed by law.”
3) “The Company complies with all applicable federal and state wage and hour laws and regulations. To satisfy these requirements, all non-exempt employees must accurately record their hours worked each day. At the end of each week, the team member and their supervisor must sign the time sheet attesting to its correctness before forwarding it to the Company Payroll Department. The Company prohibits all non-exempt employees from performing any work without recording their time for payroll purposes (i.e., ‘working off the clock’). No one at the Company is authorized to work off the clock and no one at the Company has the authority to require any employee to perform off-the-clock work.”
4) “The Company takes all reasonable steps to ensure that employees receive the correct amount of pay in each paycheck and that employees are paid promptly on the scheduled payday. It is also the Company’s policy to make only those deductions from pay authorized by, required by, and in accordance with applicable law. The Company must comply with all court-ordered payroll deductions and garnishments. Fees for processing involuntary deductions will be charged as allowed by law.”

  - Clause Summary: 1) This clause establishes payroll compliance obligations tied to accurate timekeeping, supervisor verification, and prohibition of off-the-clock work. It directly relates to certified payroll accuracy and reporting obligations required under federal/state laws.
2) Specifies compliance with payroll deductions and garnishments, requiring adherence to legal orders and regulatory payroll compliance frameworks.
3) This clause imposes certified payroll and recordkeeping obligations requiring employees and supervisors to ensure timekeeping accuracy, with prohibitions on off-the-clock work and mandatory submission of verified time sheets.
4) This clause requires accurate payroll accounting, compliance with lawful deductions, and adherence to garnishment orders, supporting certified payroll compliance principles.

  - Risk Triggers Identified: 1) Risk of inaccurate payroll submissions if hours are not properly recorded. Exposure to liability for wage-and-hour violations (federal/state). Fraudulent or falsified time records leading to penalties. 
2) Improper handling of garnishments or deductions may expose the Company to penalties. Passing administrative fees to employees may create employee-relations conflicts. 
3) Employee misreporting or falsification of time records. Supervisors failing to enforce accurate timekeeping. Risk of wage and hour law violations from off-the-clock work. 
4) Improper deductions or failure to comply with garnishment orders. Payroll calculation errors undermining certified payroll reports. Exposure to wage claims for non-compliance with federal/state deduction laws.

  - Flow-Down Obligations: 1) Subcontractors and lower-tier labor providers must maintain equivalent timekeeping, reporting, and certification of payroll compliance to meet prime contract obligations.
2) Subcontractors must likewise comply with legal deductions and garnishments where applicable and maintain proper payroll reporting.
3) Subcontractors must adopt equivalent certified payroll processes: accurate daily timekeeping, weekly supervisor certification, and prohibition of off-the-clock work.
4) Subcontractors must ensure payroll accuracy, lawful deductions, and garnishment compliance in their payroll systems.

  - Redline Recommendations: 1) Add explicit reference to “Certified Payroll Reports” under Davis-Bacon or equivalent prevailing wage laws to avoid ambiguity. Require electronic record retention for auditability. Clarify disciplinary process to include corrective payroll adjustments, not just termination. 
2) Clarify that deductions will not reduce wages below statutory minimums. Explicitly reference compliance with the Consumer Credit Protection Act (CCPA) and state-specific garnishment laws. 
3) Insert explicit requirement for retention of payroll records in compliance with Davis-Bacon and applicable federal/state laws. Define minimum retention periods (e.g., 3 years for federal compliance). Add clear audit rights for owner/agency regarding payroll records. 
4) Specify alignment with Davis-Bacon and prevailing wage requirements for federal/state funded projects. Require subcontractor payroll records to be made available for owner/agency inspection.

  - Harmful Language / Policy Conflicts: 1) Absence of explicit linkage to prevailing wage and certified payroll compliance could weaken enforceability. No timeline for retention of payroll records is specified (potential conflict with federal 3-year minimum and state longer retention rules).
2) Charging employees processing fees, while legally permissible, could conflict with employee protection policies and lead to disputes. 
3) Lack of explicit certified payroll submission requirement to funding/oversight agencies (only internal reporting noted). Ambiguity in enforcement standards—unclear penalties for supervisors who fail to comply. 
4) No provision addressing certified payroll form submission (e.g., WH-347 for Davis-Bacon). Cost recovery of garnishment fees passed to employees may conflict with state wage laws.

- Prevailing Wage, Davis-Bacon & Federal/State Wage Compliance

  - Clause Language: 1) “Contractor shall comply with all applicable wage and hour laws, including the Davis-Bacon Act, state prevailing wage statutes, and related federal, state, and local regulations. Contractor shall submit weekly payrolls as required, maintain records for not less than three years, and make such records available for inspection by the OWNER, the ENGINEER, and regulatory agencies. Noncompliance may result in withholding of payments, termination, or other remedies available under law.”
2) “Contractor shall ensure that all payroll amounts are correct, lawful deductions are applied, and that garnishment orders are processed in compliance with federal and state law.”
3) “The Company complies with all applicable federal and state wage and hour laws and regulations. To satisfy these requirements, all non-exempt employees must accurately record their hours worked each day. At the end of each week, the team member and their supervisor must sign the time sheet attesting to its correctness before forwarding it to the Company Payroll Department.”

  - Clause Summary: 1) This clause establishes mandatory compliance with Davis-Bacon and state prevailing wage requirements. It requires weekly certified payroll submissions, recordkeeping, and grants inspection rights to oversight authorities.
2) This clause requires compliance with wage deduction and garnishment laws, ensuring accurate wage payments to employees under prevailing wage standards.
3) This clause establishes that the Company is obligated to comply with federal and state wage laws, which would encompass Davis-Bacon and prevailing wage compliance requirements. It mandates accurate daily timekeeping and supervisory certification of timesheets.

  - Risk Triggers Identified: 1) Failure to comply with Davis-Bacon or state prevailing wage requirements. Late or inaccurate payroll submissions leading to payment withholding. Owner’s broad authority to inspect and penalize for wage noncompliance. 
2) Incorrect wage deductions leading to legal violations. Noncompliance with garnishment orders. Conflicts with federal or state prevailing wage enforcement audits. 
3) Misreporting or underreporting hours worked. Failure to comply with prevailing wage or Davis-Bacon requirements during federally or state-funded projects. Lack of supervisory oversight or improper certification of time records. Exposure to Department of Labor audits, back wage liability, and penalties for non-compliance.

  - Flow-Down Obligations: 1) Subcontractors must adhere to Davis-Bacon and prevailing wage laws, submit weekly payrolls, and allow inspection of wage records by project owners and agencies.
2) Subcontractors must comply with wage deduction and garnishment laws and ensure that payroll reflects accurate prevailing wage compliance.
3) Subcontractors on federally or state-funded projects must also comply with Davis-Bacon and prevailing wage rules. Flow-down requires ensuring subcontractors adopt the same timekeeping, reporting, and wage compliance standards. Contractor must verify subcontractor payroll records and certifications.

  - Redline Recommendations: 1) Clarify inspection rights to apply only to relevant payroll records (avoid overbroad access). Limit penalties to proportionate remedies for actual wage violations. Require advance notice before withholding payments for noncompliance. 
2) Require OWNER oversight only where legally mandated (to avoid duplicative enforcement). Clarify scope of “compliance” to avoid contractor liability for unforeseeable employee legal disputes. 
3) Explicitly reference Davis-Bacon Act and applicable state prevailing wage statutes to avoid ambiguity. Require certified payroll reporting in compliance with Department of Labor standards (e.g., WH-347 form). Include audit rights for the Company to review subcontractor payroll records. Clarify that violations by subcontractors are grounds for termination or back-charge. Strengthen supervisory responsibility by requiring electronic or auditable timekeeping systems.

  - Harmful Language / Policy Conflicts: 1) Broad inspection rights without limits may create privacy/confidentiality issues. Owner’s unilateral withholding rights create financial instability for the contractor. Ambiguity in “other remedies” could expose the contractor to disproportionate consequences. 
2) Overly broad contractor liability for wage deductions may extend beyond statutory requirements. Could expose contractor to liability for third-party administrative errors outside its control. 
3) Current language is general and does not explicitly name prevailing wage or Davis-Bacon compliance, creating compliance risk if audited. No mention of record retention periods, which is a statutory requirement under Davis-Bacon (3 years). No explicit prohibition against retaliation for reporting wage violations—potential conflict with compliance best practices.

- EEO, Non-Discrimination, MWBE/DBE Participation Requirements

  - Clause Language: 1) “The Contractor shall comply with all applicable federal, state, and local laws and regulations pertaining to Equal Employment Opportunity (EEO) and non-discrimination. The Contractor shall not discriminate against any employee or applicant for employment because of race, color, religion, sex, national origin, age, disability, or other protected classification. In addition, the Contractor shall make good faith efforts to include Minority and Women-Owned Business Enterprises (MWBEs) and Disadvantaged Business Enterprises (DBEs) in subcontracting opportunities.”
2) “Contractor shall maintain and post in conspicuous places available to employees and applicants, notices provided by the federal and state agencies setting forth the provisions of this non-discrimination policy. Records of hiring, promotion, and subcontracting decisions shall be maintained and made available for audit upon request.”
3) “Atlantic Pipe Services is committed to creating and maintaining a workplace in which all team members have an opportunity to participate and contribute to the success of the business and are valued for their skills, experience, and unique perspectives. This commitment is embodied in company policy and the way we do business at Atlantic Pipe Services and is an important principle of sound business management.”

  - Clause Summary: 1) This clause imposes obligations on the Contractor to follow all EEO and non-discrimination requirements, and mandates proactive inclusion of MWBEs and DBEs in project participation.
2) Requires contractors to display required notices, maintain records, and allow audits to verify compliance with EEO and non-discrimination laws.
3) This clause affirms the company’s policy of equal employment opportunity and non-discrimination, committing to diversity, inclusion, and respect for all employees’ skills and backgrounds.

  - Risk Triggers Identified: 1) Noncompliance with EEO or anti-discrimination laws. Failure to document or demonstrate good-faith efforts toward MWBE/DBE participation. Potential loss of federal or state funding for violations. 
2) Failure to post notices or maintain records. Non-cooperation with audits. Exposure to fines or penalties for recordkeeping violations. 
3) Failure to implement non-discrimination practices may lead to civil rights violations. Lack of tracking for MWBE/DBE participation could expose the company to non-compliance with state/federal contract requirements. Absence of clear enforcement or reporting mechanisms may weaken compliance.

  - Flow-Down Obligations: 1) Subcontractors must be bound to the same EEO, non-discrimination, and MWBE/DBE participation requirements. The prime contractor must monitor compliance and provide documentation of subcontractor participation.
2) Subcontractors must also post notices and maintain employment records as required. The contractor is responsible for ensuring subcontractor compliance.
3) Subcontractors must also adhere to EEO and non-discrimination commitments, ensuring no exclusion of MWBE/DBE participation in federally or state-funded projects.

  - Redline Recommendations: 1) Specify clear participation goals or percentage targets for MWBE/DBE inclusion. Require periodic reporting to document compliance and good-faith efforts. Clarify remedies or penalties if MWBE/DBE participation requirements are not met. 
2) Limit audit rights to relevant employment and subcontracting records. Define retention period for records to prevent indefinite obligations. 
3) Add explicit reference to compliance with Title VII, EEOC regulations, and applicable state non-discrimination laws. Incorporate measurable MWBE/DBE participation goals where contractually required. Require subcontractors to certify compliance with EEO and MWBE/DBE participation obligations.

  - Harmful Language / Policy Conflicts: 1) Broad obligations without defined targets may create uncertainty and disputes. Vague “good faith” language could be deemed insufficient by regulatory agencies if not supported with measurable criteria. 
2) Overly broad audit rights may create privacy and confidentiality risks. Lack of limits on record retention could conflict with company data retention policies. 
3) Current clause is aspirational and lacks enforceable compliance mechanisms. No mention of federal/state reporting requirements for EEO or MWBE/DBE, which may conflict with public contract obligations.

- Anti-Lobbying / Cone of Silence Provisions

  - Clause Language: Not present in contract.

  - Clause Summary: No provisions were found in the contract text or incorporated FDOT specifications addressing restrictions on lobbying, political advocacy, or “cone of silence” rules prohibiting communications with agency officials during procurement or contract performance.

  - Risk Triggers Identified: N/A – no clause discovered.

  - Flow-Down Obligations: N/A – no clause discovered.

  - Redline Recommendations: Since this clause is absent, the recommendation is to insert standard anti-lobbying language (consistent with 31 U.S.C. §1352 and FDOT procurement protocols) to mitigate risks of improper influence or violations of procurement law.

  - Harmful Language / Policy Conflicts: N/A – no clause discovered.

- Apprenticeship, Training & Workforce Development Requirements

  - Clause Language: 1) “Atlantic Pipe Services (APS) has grown by using follow-along and on-site training; this SOP documents training processes to maintain quality and consistency. An employee hired by APS will undergo training as outlined in this document. Each role listed in Table 1 – Training and Tasks by Role, includes the required training and high-level tasks for each role; it also includes considerations and skills necessary for hiring or promotion.”
2) “Supervisors check if employees are competent based on training criteria. Most roles don’t have formal task lists. As teams grow, they should document common tasks for each role. An example is provided in Appendix A.”

  - Clause Summary: 1) This provision establishes internal workforce development requirements through structured apprenticeship-style training programs, role-specific tasks, and competency evaluations for hiring and advancement.
2) This clause requires supervisors to evaluate employee competency against training criteria but acknowledges the absence of formal task lists for many roles, leaving responsibility for documenting tasks as teams expand.

  - Risk Triggers Identified: 1) Lack of defined minimum standards for training quality. Possible inconsistency in training delivery across roles or sites. Risk of liability if untrained workers perform regulated tasks. 
2) Training effectiveness depends on subjective supervisor evaluations. Absence of formalized task lists creates inconsistency in workforce competency assessments. Potential disputes regarding adequacy of training when errors occur.

  - Flow-Down Obligations: 1) Subcontractors or workforce partners must ensure comparable training standards for employees fulfilling contract work to maintain compliance with APS’s competency requirements.
2) Supervisors and subcontractor managers must ensure clear documentation of training outcomes and establish task lists for consistent workforce development.

  - Redline Recommendations: 1) Define minimum training hours and certification requirements by role. Require documentation and verification of competency assessments. Add language requiring subcontractors to align with APS’s workforce training standards. 
2) Require creation of formal task lists for all roles. Standardize evaluation methods and criteria for competency checks. Ensure documentation is maintained and auditable.

  - Harmful Language / Policy Conflicts: 1) Current clause lacks enforceable timelines or independent verification, risking insufficient workforce preparation. “Follow-along” and “on-site training” may not meet formal apprenticeship or FDOT workforce development requirements. 
2) Reliance on informal or ad hoc documentation may create compliance gaps. Lack of oversight mechanisms could lead to workforce underqualification.

- Immigration / E-Verify Compliance Obligations

  - Clause Language: 1) “This employer participates in E-Verify and will provide the federal government with your Form I-9 information to confirm that you are authorized to work in the U.S. If E-Verify cannot confirm that you are authorized to work, this employer is required to give you written instructions and an opportunity to contact the Department of Homeland Security (DHS) or Social Security Administration (SSA) so you can begin to resolve the issue before the employer can take any action against you, including terminating your employment. Employers can only use E-Verify once you have accepted a job offer and completed the Form I-9.”
2) “This employer participates in E-Verify and will provide the federal government with your Form I-9 information to confirm that you are authorized to work in the U.S. If E-Verify cannot confirm that you are authorized to work, this employer is required to give you written instructions and an opportunity to contact Department of Homeland Security (DHS) or Social Security Administration (SSA) so you can begin to resolve the issue before the employer can take any action against you, including terminating your employment. Employers can only use E-Verify once you have accepted a job offer and completed the Form I-9.”
3) “Immigration Law Compliance. The Company is committed to employing only individuals who are authorized to work in the United States and does not unlawfully discriminate on the basis of citizenship or national origin. As a condition of employment, every employee must properly complete, in a timely manner, the Form I-9 and provide valid documentation establishing identity and employment eligibility.”

  - Clause Summary: 1) The employer mandates compliance with federal employment verification requirements by using the DHS E-Verify system. It requires employee data submission for work authorization verification and provides employees the opportunity to contest mismatches.
2) The employer is required to use the federal E-Verify system to confirm employment eligibility. If a worker cannot be confirmed, they must be given instructions and an opportunity to resolve discrepancies before adverse action is taken.
3) Sets mandatory requirement for Form I-9 completion for all employees, consistent with immigration law. Prohibits unlawful discrimination while enforcing compliance.

  - Risk Triggers Identified: 1) Mandatory E-Verify participation could create liability if procedures are not followed precisely. Risks of delays or wrongful termination if DHS/SSA mismatches are not resolved properly. Exposure to penalties for improper use of E-Verify outside allowed circumstances (e.g., pre-offer screening). 
2) Risk of employment termination if E-Verify fails despite valid work authorization. Potential delays in onboarding due to DHS or SSA verification backlogs. Exposure to discrimination claims if improperly applied. 
3) Improper completion or retention of I-9 forms. Risk of ICE or DHS penalties for noncompliance. Exposure to discrimination liability if improperly applied.

  - Flow-Down Obligations: 1) Subcontractors may also need to participate in E-Verify and comply with I-9 verification processes. Contractors must ensure consistent application of E-Verify rules to avoid discrimination or violations of federal employment law. 
2) Subcontractors and lower-tier employers engaged on covered projects must also adhere to E-Verify requirements and I-9 compliance.
3) Subcontractors are expected to maintain compliant hiring and verification processes under I-9 and E-Verify standards.

  - Redline Recommendations: 1) Specify that E-Verify obligations apply only where required by law or federal funding requirements. Include clear process timelines for mismatch resolution and employer obligations. State that subcontractors must independently comply with E-Verify rules if required. 
2) Add language ensuring no adverse action is taken until final DHS/SSA resolution is complete. Clarify employer’s obligation to notify employees promptly of tentative non-confirmations. Require subcontractor compliance to be documented as a condition of contract award. 
3) Specify exact retention period for I-9 documentation. Require periodic internal audits to verify compliance. Include explicit subcontractor certification obligations.

  - Harmful Language / Policy Conflicts: 1) Broad requirement to use E-Verify may create undue administrative burdens. Risk of discriminatory practices if E-Verify is applied inconsistently. No carve-out for jurisdictions where E-Verify is not mandatory. 
2) No explicit protection against misuse of E-Verify beyond statutory minimums. No clear enforcement mechanism for subcontractors’ compliance obligations. Risks overlap with EEO/Non-Discrimination provisions (possible double classification but primary fit is here). 
3) No explicit audit or oversight language for subcontractor compliance. Risk of uneven enforcement without clear flow-down monitoring.

- Worker Classification & Independent Contractor Restrictions

  - Clause Language: 1) “Hazard Communication Training shall be provided by the independent contractor to their team members in accordance with all federal (OSHA), state and local rules, and regulations. They must also ensure that they have SDSs for chemicals brought on-site as well as be able to provide Atlantic Pipe Services with copies of SDSs upon request.”
2) “Hazard Communication Training shall be provided by the independent contractor to their team members in accordance with all federal (OSHA), state and local rules, and regulations. They must also ensure that they have SDSs for chemicals brought on-site as well as be able to provide Atlantic Pipe Services with copies of SDSs upon request.”

  - Clause Summary: 1) This clause establishes compliance obligations for independent contractors, requiring them to train their workers on hazard communication standards and maintain Safety Data Sheets (SDSs) for any chemicals they bring onsite. Contractors must also provide SDSs to Atlantic Pipe Services upon request.
2) Independent contractors are responsible for OSHA-compliant training and hazard communication for their employees, including provision and availability of Safety Data Sheets (SDSs) for all chemicals introduced on-site.

  - Risk Triggers Identified: 1) Failure of independent contractors to provide required training. Contractors not maintaining or providing SDSs. Potential OSHA violations and regulatory fines. Liability transfer risks to Atlantic Pipe Services if contractors are noncompliant. 
2) Misclassification of workers could allow contractors to shift safety obligations improperly. Contractors may fail to comply with OSHA if independent status is used as a loophole. Lack of SDS provision creates regulatory non-compliance risks.

  - Flow-Down Obligations: 1) Independent contractors are directly obligated to comply with OSHA, state, and local rules. Contractors must ensure their workers receive training and comply with hazard communication standards. Contractors must provide documentation (SDSs) to the hiring entity on demand. 
2) Subcontractors and independent contractors must independently train their employees and provide SDS documentation. Main contractor may be exposed to liability if oversight is inadequate.

  - Redline Recommendations: 1) Clarify explicit consequences for noncompliance (e.g., suspension of work, termination of contract). Add a verification process requiring contractors to certify training completion and SDS compliance prior to work. Insert language requiring indemnification if contractor’s failure leads to fines or penalties. 
2) Insert explicit verification rights for the Owner/Prime Contractor to confirm compliance. Add language requiring independent contractors to indemnify for OSHA non-compliance tied to classification. Require submission of training certifications and SDS records before site mobilization.

  - Harmful Language / Policy Conflicts: 1) No explicit enforcement or penalties for noncompliance; enforcement is implied but not detailed. The clause places responsibility solely on independent contractors, which may not be enforceable without a clear verification mechanism. Lack of defined remedies may conflict with internal compliance standards or company risk controls. 
2) Clause shifts compliance burden entirely onto independent contractors without mandating oversight, risking exposure under joint-employer rules. No safeguard for Owner/Prime Contractor if independent contractors fail to comply.

- Drug-Free Workplace Programs & Substance Testing Requirements

  - Clause Language: 1) “Drug-Free Workplace. No employee may consume or possess alcohol, or use, possess, sell, purchase, or transfer illegal drugs… No employee may report to work with illegal drugs (or their metabolites) or alcohol in his or her bodily system… Any violation of this policy will result in disciplinary action, up to and including immediate termination of employment. Pre-Employment Drug Testing. All applicants… are subject to submitting to pre-hire drug testing once a conditional offer… has been made. The Company may condition employment offers on the successful completion and passing of a drug screening administered by the Company or a Florida licensed independent testing facility of the Company’s choice.”
2) “Reasonable Suspicion Testing. If the Company has a reasonable suspicion… the Company reserves the right to have the employee undergo drug and/or alcohol testing… Post-Incident Testing… employees who violate safety or security procedures or who are in work-related accidents [may be] subject to drug and alcohol testing. Procedures… will be administered internally or through a Florida licensed independent testing facility. The Company will pay the cost of the test.”
3) “Testing will be performed… pursuant to Florida Statute §440.101 & §440.102 and Chapter 59A-24 Drug-Free Workplace Standards, including Job Applicant, Reasonable Suspicion, Routine Fitness for Duty, and Follow-up Drug Testing. The company may test for [a wide panel of drugs and alcohol]… Any team member determined to be in violation… is subject to disciplinary action, which may include termination, even for the first offense.”
4) “All current team members are subject to controlled substance abuse screening… If follow-up testing… is required, testing will be conducted at least once a year for 2 years… Random testing may be conducted… Employees subject to FHWA regulations will be tested according to SAMHSA protocols.”

  - Clause Summary: 1) Establishes a zero-tolerance drug and alcohol policy, including pre-employment drug testing as a condition of hire. Violations result in discipline up to termination.
2) Authorizes drug/alcohol testing under reasonable suspicion or post-incident scenarios, with employer paying for tests.
3) Defines statutory compliance framework for drug testing, including multiple testing scenarios. Lists substances subject to screening.
4) Outlines random and follow-up testing requirements, with FHWA- and SAMHSA-aligned testing standards for DOT-regulated drivers.

  - Risk Triggers Identified: 1) Any employee use/possession of drugs or alcohol on premises or while working. Testing positive in pre-employment screenings. Reporting to work under influence. 
2) Reasonable suspicion of impairment. Workplace accidents or safety/security violations. 
3) Positive drug/alcohol test under any of the enumerated testing conditions. Refusal to comply with required testing. 
4) Assignment to safety-sensitive roles. Random or follow-up testing under company/EAP protocols.

  - Flow-Down Obligations: 1) No explicit flow-down noted, but vendors, clients, and visitors are also subject to policy compliance while on premises.
2) None specified.
3) None explicitly, though compliance with Florida statute may impose regulatory reporting.
4) Contractors performing DOT-regulated transport must comply with FHWA/SAMHSA standards.

  - Redline Recommendations: 1) Clarify alignment with applicable Florida and federal labor laws to prevent challenges. Include rehabilitation/assistance options before termination (mitigation option). Limit employer discretion in medical marijuana treatment to avoid ADA conflict. 
2) Require documentation of “reasonable suspicion” to avoid abuse. Add employee rights for independent verification or appeal of results. Define “post-incident” criteria clearly (injury thresholds, property damage, etc.). 
3) Provide rehabilitation/assistance options as an alternative to first-offense termination. Ensure list of drugs remains updated with statutory definitions (avoid overbreadth). Clarify privacy safeguards in compliance with HIPAA.
4) Limit random testing scope to safety-sensitive positions to avoid privacy challenges. Clarify protections for employee confidentiality. Allow independent retesting at employee’s expense.

  - Harmful Language / Policy Conflicts: 1) Broad discretion may conflict with state protections for prescription medication and medical marijuana. “Immediate termination” language could conflict with progressive discipline policies or bargaining agreements. 
2) Lack of defined criteria for suspicion introduces risk of arbitrary enforcement or discrimination claims. Internal administration of tests (instead of external labs only) may raise chain-of-custody and confidentiality concerns. 
3) “Termination for first offense” language creates rigidity and potential conflict with federal labor law protections. Risk of ADA conflict if medical marijuana or prescribed opioids are not excepted. 
4) Mandatory random testing for all employees (not just DOT-regulated) may exceed legal limits in some jurisdictions. Follow-up testing requirements without clear employee consent could create legal exposure.

## VI. Data, Technology & Deliverables

- Data Ownership, Access & Rights to Digital Deliverables

  - Clause Language:  1) “The CONTRACTOR acknowledges that all data, reports, drawings, specifications, and other deliverables developed under this Contract are the property of the OWNER. The OWNER shall have full rights of use, reproduction, and distribution without restriction.”
2) “At final completion, the CONTRACTOR shall deliver to the OWNER all digital files, including as-built drawings, GIS data, and electronic reports, in formats specified by the Contract Documents. No final payment shall be made until all such deliverables are received.”
3) “Data provided by the OWNER or generated through project activities shall remain the exclusive property of the OWNER. The CONTRACTOR shall not claim any ownership interest or assert intellectual property rights over FDOT-supplied or project-generated data.”
4) “The OWNER reserves the right to access, audit, and reproduce any project records, data, or digital deliverables developed or maintained by the CONTRACTOR in connection with this Contract, both during performance and after completion.”

  - Clause Summary: 1) Transfers ownership of all contract-created data and digital deliverables to the Owner, granting unrestricted rights of use.
2) Requires contractor to provide all digital deliverables at project closeout as a condition of final payment.
3) Restricts contractors from asserting ownership over FDOT/Owner-provided or generated data.
4) Provides the Owner with broad audit and access rights over project data and deliverables.

  - Risk Triggers Identified: 1) Contractor loss of intellectual property rights. Broad Owner rights without compensation for reuse. Risk of dispute if contractor’s proprietary tools/data are used. 
2) Payment withholding if deliverables are delayed. Risk of disputes over file formats or completeness. 
3) Contractor prevented from using project-generated data for future projects. No allowance for derivative works created by contractor. 
4) Potential confidentiality breaches if contractor’s internal data are exposed. Owner’s access rights extend post-completion.

  - Flow-Down Obligations: 1) Subcontractors must acknowledge Owner’s ownership of data and deliverables produced under their scope.
2) Subcontractors producing data/deliverables must provide them to contractor in contract-specified formats.
3) Subcontractors must disclaim ownership of Owner-provided or generated data.
4) Subcontractors must maintain accessible, auditable records and provide them to contractor/Owner.

  - Redline Recommendations: 1) Add carve-out for contractor’s pre-existing intellectual property. Clarify scope of “other deliverables” to avoid overreach. 
2) Specify acceptable file formats and delivery methods. Allow partial payment if non-critical deliverables are pending. 
3) Allow contractor limited license to use anonymized or derivative project data for training/improvement.
4) Limit audit rights to contract-relevant data. Add confidentiality protections for contractor proprietary data.

  - Harmful Language / Policy Conflicts: 1) Unlimited Owner use may conflict with contractor’s proprietary methods. No protection for confidential or sensitive contractor information. 
2) “No final payment” clause creates leverage imbalance. Ambiguity on “formats specified” could lead to disputes. 
3) Overly restrictive; blocks reuse of data that could benefit contractor’s future work.
4) Broad audit powers may create conflicts with data privacy obligations. No time limit specified on post-completion access.

- AI / Technology Use Restrictions (Automation, Digital Tools, Proprietary Systems)

  - Clause Language: Not present in contract.

  - Clause Summary: No clause was identified that restricts or governs the use of artificial intelligence, automation tools, digital platforms, or proprietary systems in the performance of work or deliverables.

  - Risk Triggers Identified: Absence of guidance on AI or digital tool usage may allow contractors to employ unapproved or insecure technologies. Potential for misuse of proprietary systems without contractual boundaries.

  - Flow-Down Obligations: None applicable, as no clause is present.

  - Redline Recommendations: Insert a clause clarifying whether AI, automation, or other digital technologies may be used, including security and intellectual property safeguards. Require disclosure of all digital tools and proprietary systems used on the project. Mandate pre-approval for AI-driven deliverables or proprietary system integrations.

  - Harmful Language / Policy Conflicts: None identified, as no language is present.

- Digital Surveillance, GIS-Tagged Deliverables & Monitoring Requirements

  - Clause Language: 1) “The pictures will be taken with a GPS camera that automatically geotags the picture… A caption under each photograph shall include: Photograph number, description, date, location and direction of view, and state plane coordinates. All photographs included in the drawings will also be provided to CITY in JPEG format on digital media.”
2) “Digital Images shall include aerial photograph / digital images showing the entire construction area. Deliver digital images to the ENGINEER to accompany each Application for Payment.”
3) “The CONTRACTOR shall submit digital progress AS-BUILT DRAWINGS with each application for payment. These DRAWINGS shall accurately depict the WORK completed and for which payment is being requested… Drawings shall include color photographs of all connections to existing CITY infrastructure as well as all critical utility crossings and where specifically required on the design drawings.”

  - Clause Summary: 1) Contractors are required to use GPS-enabled cameras to capture and geotag project photographs, include metadata (date, location, coordinates, etc.), and deliver both printed and digital copies for official project records.
2) Contractors must provide aerial or digital surveillance images documenting the construction site and deliver them with each payment application.
3) Contractors must submit digital progress as-builts, including GIS-referenced photographs of utility connections, crossings, and critical features, with each payment request.

  - Risk Triggers Identified: 1) Failure to use GPS/geotagging as required. Missing or inaccurate metadata (coordinates, date, location). Non-compliance in format delivery (JPEG, labeling). 
2) Failure to provide aerial surveillance images. Submission of incomplete or low-quality coverage of the construction site. 
3) Failure to submit timely GIS-linked as-built updates. Incomplete photographic evidence of critical utility work. Misrepresentation of project progress tied to payment.

  - Flow-Down Obligations: 1) Subcontractors performing photographic documentation must adhere to GPS/geotagging requirements, metadata inclusion, and electronic submittal standards.
2) Any subcontractor conducting aerial photography must provide full coverage and comply with digital media delivery standards.
3) Surveyors, subcontractors, or utility crews providing as-built data must comply with digital and GIS-photo documentation requirements.

  - Redline Recommendations: 1) Subcontractors performing photographic documentation must adhere to GPS/geotagging requirements, metadata inclusion, and electronic submittal standards.
2) Require minimum technical specifications for aerial imagery (resolution, scale). Mandate certification of image authenticity. Include retention and access requirements for surveillance data. 
3) Require timestamping and geotagging for all photographs linked to as-builts. Add third-party verification or engineer signoff for GIS/photo accuracy. Include audit rights for CITY to verify alignment between payment requests and digital submissions.

  - Harmful Language / Policy Conflicts: 1) No security or privacy restrictions on GPS data sharing may raise confidentiality risks. Absence of explicit limits on secondary use of images by the CITY or third parties could conflict with internal data governance policies. 
2) Absence of limitations on secondary distribution of aerial imagery may conflict with data security obligations. Potential privacy concerns if surrounding non-project property is captured in aerial surveillance. 
3) No explicit retention or data integrity safeguards for GIS/as-built photographs. Risk of payment disputes if as-builts lack standardized validation procedures.

- GIS, Digital Workflow Integration & Electronic Submittals

  - Clause Language: 1) “Contractor shall submit all project documentation in electronic format as specified by the OWNER, compatible with agency digital workflow systems. All digital deliverables must comply with the OWNER’s electronic submittal standards, including format, metadata, and GIS integration requirements.”
2) “All GIS-enabled data and mapping deliverables shall be submitted in a format compatible with the CITY’s enterprise GIS system. Deliverables shall include spatial metadata, attribute data, and comply with applicable federal and state GIS standards.”
3) “Electronic submittals shall be the official record of project deliverables. Contractor shall ensure electronic submittals are complete, accurate, and consistent with contract requirements prior to transmission. Paper copies, where required, are considered supplementary only.”

  - Clause Summary: 1) Requires the contractor to provide all project deliverables electronically, in compliance with agency digital workflow systems and GIS compatibility standards.
2) Mandates GIS deliverables be formatted for compatibility with the CITY’s enterprise system and federal/state GIS requirements, including metadata and attribute data.
3) Designates electronic submittals as the official project record, with paper copies secondary, and requires contractors to validate completeness and accuracy before submission.

  - Risk Triggers Identified: 1) Non-compliance with electronic format standards may delay approvals. Incompatibility with GIS integration requirements could prevent acceptance of deliverables. Metadata errors or omissions could undermine project record integrity. 
2) Ambiguity on “applicable federal and state GIS standards” could create compliance uncertainty. Rejection of deliverables due to format incompatibility with CITY’s system. Increased costs if re-submittals are required to align with CITY standards. 
3) Contractor assumes liability for accuracy of all electronic submissions. Potential disputes if OWNER later deems submittals incomplete despite contractor validation. Paper copies may not be considered authoritative in disputes.

  - Flow-Down Obligations: 1) Subcontractors must ensure digital deliverables are in required formats, include necessary metadata, and comply with GIS compatibility requirements.
2) Subcontractors providing GIS data must adhere to CITY compatibility requirements and ensure metadata/attribute data compliance.
3) Subcontractors providing documentation must deliver digital versions that can serve as official project records.

  - Redline Recommendations: 1) Specify accepted electronic formats and GIS standards to avoid ambiguity. Require OWNER to provide written confirmation of software/version requirements. Clarify turnaround time for OWNER acceptance or rejection of electronic submissions. 
2) Define explicitly which GIS standards apply (e.g., FGDC, state-specific). Require CITY to provide specifications on acceptable formats. Add cure period for deliverable resubmissions at no additional cost. 
3) Insert language requiring OWNER review and acceptance before electronic submittals are deemed final. Preserve equal evidentiary weight for paper copies in case of digital system failure. Require clear protocols for correction of identified submission errors.

  - Harmful Language / Policy Conflicts: 1) Broad OWNER discretion to reject submissions without clear criteria may create unfair risk. Lack of detail on acceptable GIS platforms may cause unnecessary rework and costs. 
2) Lack of clear format/standard definition shifts excessive risk to contractor. Opens risk of inconsistent enforcement if CITY changes GIS standards mid-project. 
3) Exclusive reliance on electronic records could conflict with state rules requiring retention of paper records. Overbroad contractor liability for “complete and accurate” submittals without OWNER verification mechanisms.

- Confidentiality, Data Security & Records Retention Obligations

  - Clause Language: 1) “Protecting the Company’s confidential and proprietary business information and trade secrets is vital to its interests and success. ‘Confidential and Proprietary Information’ means any and all confidential and/or proprietary knowledge, data or information of the Company… All Confidential and Proprietary Information owned, developed, or acquired by the Company shall remain the sole and exclusive property of the Company.”
2) “Employees are advised that pursuant to the Defend Trade Secrets Act an individual will not be held criminally or civilly liable… for the disclosure of a trade secret that is made in confidence to a government official or attorney for the purpose of reporting or investigating a suspected violation of law…”
3) “The Company will treat all drug testing-records as confidential as required by law. The Company will not disclose the results of the test without the employee’s consent or a court order.”

  - Clause Summary: 1) Defines “Confidential and Proprietary Information,” mandates its protection, prohibits disclosure or misuse, and affirms sole company ownership of such data.
2) Provides statutory notice that whistleblowers disclosing trade secrets to regulators or in sealed legal filings are protected from liability.
3) Ensures confidentiality of employee drug test results, restricting disclosure to consented or legally mandated circumstances.

  - Risk Triggers Identified: 1) Broad and undefined scope of “confidential” information. Disciplinary action and legal liability attached to violations. No exceptions for whistleblowing or compelled disclosures (unless separately governed). 
2) Invokes statutory protections but may not be clearly integrated with other confidentiality policies. Risk if not properly highlighted in employee communications. 
3) Confidentiality tied strictly to legal requirements; no internal retention limits identified. May create exposure if retention is indefinite.

  - Flow-Down Obligations: 1) Contractors, subcontractors, and employees with access to confidential information may need parallel nondisclosure obligations.
2) Subcontractors and vendors handling proprietary data should also provide DTSA notice to employees in agreements.
3) Vendors conducting drug testing must implement equivalent confidentiality safeguards.

  - Redline Recommendations: 1) Narrow the scope of “Confidential Information” to exclude publicly available or independently developed information. Insert carve-outs for legally required disclosures. Clarify limits of liability for unintentional disclosure. 
2) Ensure this provision is prominently referenced in all confidentiality-related sections. Align with state whistleblower laws for broader protection. 
3) Specify record retention period and destruction protocol. Clarify scope of “confidential” to include storage, transmission, and access controls.

  - Harmful Language / Policy Conflicts: 1) Overly expansive confidentiality definition could conflict with employee rights under whistleblower protections. “Sole and exclusive property” clause may conflict with collaborative IP rights under joint ventures. 
2) No direct harmful language; aligns with federal law. Risk if not harmonized with company’s broader confidentiality clause enforcement.
3) Omits security/retention standards for sensitive medical data. Could conflict with data minimization principles under evolving privacy regulations.

- Intellectual Property, Licensing & Ownership of Work Product

  - Clause Language: 1) “Except for materials indicated to be stockpiled or to remain on owner’s property, cleared materials shall become the CONTRACTOR’s property and shall be removed from the site.”
2) “All Confidential and Proprietary Information owned, developed, or acquired by the Company shall remain the sole and exclusive property of the Company… Employees may not disclose or improperly use such information, subject to discipline and legal action.”
3) “Employees are advised that pursuant to the Defend Trade Secrets Act… disclosure of a trade secret may be made in confidence to a government official or attorney for the purpose of reporting a suspected violation of law.”

  - Clause Summary: 1) Ownership of certain materials (e.g., debris, cleared items) transfers to the contractor, establishing a property right in work-product derived from site activities.
2) Confidential and proprietary information, including inventions, research, designs, and data, is owned exclusively by the company. Employees must protect this information from disclosure or misuse.
3) Provides statutory notice that employees are protected from liability when disclosing trade secrets in limited contexts, such as whistleblowing or court filings under seal.

  - Risk Triggers Identified: 1) Contractor claims ownership over project by-products. Ambiguity if materials have salvage/reuse value. No express limit on contractor’s right to resell or repurpose cleared items. 
2) Broad definition of proprietary information captures virtually all employee-created work product. Legal exposure for employees even absent personal gain. Potential misalignment with contractor-developed intellectual property. 
3) Limited scope; does not protect disclosures made outside statutory framework. Potential tension with confidentiality clauses if employees misunderstand safe-harbor.

  - Flow-Down Obligations: 1) Contractor must ensure subcontractors comply with removal/ownership provisions for cleared materials.
2) Subcontractors and employees must treat all proprietary data and work product as property of the company.
3) Contractor must ensure employees and subcontractors receive DTSA notice to preserve enforceability of nondisclosure agreements.

  - Redline Recommendations: 1) Specify that ownership transfer excludes sensitive or potentially hazardous materials. Require contractor to notify Owner before resale or reuse. Add express disclaimer of any intellectual property or design ownership by contractor in cleared items. 
2) Narrow the scope to information created within the scope of employment or funded by the company. Add carve-outs for employee-developed IP unrelated to company work. Ensure harmonization with third-party licensing agreements. 
3) Expand to clarify procedure for lawful disclosure. Require employees to consult legal counsel before disclosure. Add explicit reference to alignment with state whistleblower protections.

  - Harmful Language / Policy Conflicts: 1) Clause creates potential conflict with policies requiring Owner to retain title to all project-derived materials and intellectual property. No protection for Owner if cleared items contain proprietary elements.
2) Overly broad ownership claim may conflict with fair use, independent contractor rights, or external IP licensing terms. Lacks explicit return/destruction requirements upon separation.
3) If omitted, could invalidate certain nondisclosure/confidentiality enforcement under DTSA. Lack of clarity may chill protected whistleblower activity.

- Cybersecurity Standards, Breach Notification & IT System Use Policies

  - Clause Language: 1) “In the event of any security breach affecting Owner’s information systems or project data, Contractor shall notify Owner within 24 hours of discovery, provide a written incident report within 72 hours, and cooperate with Owner’s investigation, including providing access to relevant logs and system information.”
2) “Contractor and all subcontractors shall adhere to Owner’s IT system use policy, including user authentication, access control, monitoring, and restrictions on use of Owner’s networks for non-project purposes.”
3) “Contractor shall implement and maintain cybersecurity controls consistent with NIST Cybersecurity Framework or equivalent industry standards, including regular vulnerability scans, patch management, and employee training. Certification of compliance shall be provided to Owner annually.”

  - Clause Summary: 1) Establishes breach notification obligations with specific timelines and cooperation requirements for investigations.
2) Requires contractors and subcontractors to follow Owner’s IT system use policies, including authentication, access controls, and monitoring rules.
3) Imposes affirmative obligation on Contractor to adopt industry-standard cybersecurity practices and certify compliance annually.

  - Risk Triggers Identified: 1) Liability exposure if Contractor fails to meet 24-hour or 72-hour deadlines. Broad cooperation obligations may increase operational burden. Potential access to sensitive contractor systems and data logs. 
2) Violation of IT use restrictions may cause default or suspension. Monitoring of contractor activities on Owner’s network may raise privacy issues. Unilateral changes to IT use policies could impose new obligations mid-contract. 
3) Cost and administrative burden of maintaining NIST-equivalent controls. Risk of default if certification lapses or is found non-compliant. Ambiguity if Owner disputes equivalency of alternate standards.

  - Flow-Down Obligations: 1) Subcontractors must also provide timely breach notification and allow access to logs for Owner’s investigations.
2) All subcontractors must comply with Owner’s IT system access and monitoring policies.
3) Subcontractors providing IT-related services must also comply with cybersecurity standards and support certification processes.

  - Redline Recommendations: 1) Extend notification deadline from 24 to 48 hours to allow for fact-gathering. Limit log/system access to relevant portions only. Clarify responsibility for breach containment costs. 
2) Require notice before changes to IT use policies become binding. Clarify scope of monitoring to protect contractor confidential information. Carve out exceptions for incidental non-project use. 
3) Limit certification requirement to reasonable scope (exclude low-risk subcontractors). Allow self-attestation rather than third-party audits unless high-risk systems are involved. Add cure period for lapses in certification.

  - Harmful Language / Policy Conflicts: 1) Unqualified access to contractor systems may conflict with internal IT security protocols. No safe harbor for unintentional or low-impact incidents. 
2) Continuous monitoring without limits may conflict with privacy protections. Broad restrictions could hinder collaboration tools or approved communications. 
3) Mandatory NIST-equivalent compliance may exceed contractor’s existing IT frameworks. Annual certification requirement may conflict with internal IT governance cycles.

## VII. Supplemental Operational Risks

- Residual Equipment Operation & Maintenance Safety Risks

  - Clause Language: “Residual risks may nevertheless occur on use of the cutting and pipe repair robot. Risks to the owner or third parties or damage to the robot and other material assets may occur if the robot: • is operated in an improper manner, • is transported, installed, commissioned/decommissioned, maintained or cleaned in an improper manner.”

  - Clause Summary: Defines residual operational risks tied to improper handling, operation, or maintenance of specialized robotic equipment.

  - Risk Triggers Identified:   Incorrect operation, installation, or transport.   Inadequate training or safety precautions.   Exposure to wastewater hazards during cleaning/repair.

  - Flow-Down Obligations: Contractors must flow down safety and training requirements for subcontractors who use or maintain robotic equipment.

  - Redline Recommendations: Assign liability to contractor for residual operational risks. Require documented operator training/certification. Mandate periodic inspections and reporting for critical safety.

  - Harmful Language / Policy Conflicts: Vendor disclaimers may shift liability away from contractor. Lack of explicit mitigation requirements leaves project owner exposed.

## VIII. Final Analysis

Final Redline Risk Summary and Recommendations

| Risk Area | Risk Summary | APS Redline Position |
| --- | --- | --- |
| Substitution Requests (IV.7–8) | Contractor assumes liability equal to specified products; waiver of claims for unforeseen substitution costs; delays from limited substitution approval. | Strike waiver of unforeseeable costs; revise “equal or superior” to “reasonable equivalence”; allow multiple justified substitution requests. |
| Cost Recovery & Change Orders (IV.9–10) | Strict waiver language prevents recovery of unforeseen costs; excessive discretion to Owner on approvals. | Remove broad waiver clauses; require defined Owner turnaround time; narrow Owner discretion. |
| Certified Payroll & Reporting (V.1) | Risks of noncompliance with certified payroll documentation and reporting obligations. | Clarify reporting deadlines; require Owner review periods; specify penalties for noncompliance. |
| Prevailing Wage / Davis-Bacon Compliance (V.2) | FDOT may terminate work for convenience with minimal notice and no reimbursement for mobilized cost Exposure if contractor/subcontractors fail to comply with wage requirements; Owner discretion in wage interpretation. | Define wage verification process; allocate responsibility clearly; strike ambiguous wage compliance language. |
| MWBE / EEO / DBE Participation (V.3) | Risk of penalties or disqualification for failing to meet participation requirements; unclear subcontractor obligations. | Clarify participation percentage obligations; define flow-down requirements; add cure rights before penalty. |
| Anti-Lobbying / Cone of Silence (V.4) | Insurance certificate clause misclassified; vague obligations create exposure for underinsurance post-completion. | Require Owner named as additional insured; define duration (2–3 years); mandate submission before final payment. |
| Apprenticeship & Workforce Development (V.5) | Ambiguity around training/apprenticeship obligations; risk of penalties for noncompliance. | Define acceptable training programs; require written Owner acknowledgment of compliance. |
| Immigration / E-Verify (V.6) | Liability for undocumented workers or subcontractor noncompliance. | Require subcontractor certification of compliance; add cure right before termination. |
| Worker Classification (V.7) | Risk of misclassification penalties for independent contractors. | Clarify test for classification; require subcontractor indemnity for violations. |
| Drug-Free Workplace (V.8) | Strict substance testing obligations without Owner reciprocity. | Add mutuality requirement; clarify testing standards and compliance procedures. |
| Data Ownership (VI.1) | Owner claims full rights to digital deliverables; contractor restricted from use; unclear return/transfer obligations. | Clarify contractor license rights; define data return obligations; restrict FDOT access post-project. |
| AI / Technology Restrictions (VI.2) | Prohibition on certain tools or digital systems may limit efficiency. | Narrow restriction to protect proprietary systems only; carve out common industry tools. |
| GIS / Digital Surveillance (VI.3) | Mandatory GPS/geotagged deliverables create liability for metadata errors, cybersecurity risks. | Require encryption/secure transfer; define contractor liability scope; set data retention limits. |
| GIS Workflow Integration (VI.4) | Integration requirements may impose costly compliance burdens; lack of clarity on standards. | Define format/standards; require Owner to provide system specifications; allow for reimbursement of extraordinary costs. |
| Confidentiality & Data Security (VI.5) | Broad confidentiality/data retention obligations; exposure to Owner-imposed standards. | Clarify record retention periods; limit scope of confidentiality to project data only. |
| Intellectual Property (VI.6) | Contractor risks loss of work product ownership; Owner claims unlimited rights. | Carve out contractor background IP; limit license scope; require joint ownership for jointly developed IP. |
| Cybersecurity & IT Policies (VI.7) | Breach notification obligations; strict IT system use rules; compliance with Owner cybersecurity standards. | Define breach notification timelines; clarify subcontractor flow-down; negotiate reasonable IT system use policies. |
| Supplemental Risks (VII.1) | Residual risks from robotic/equipment operation and maintenance not fully addressed in other sections. | Define maintenance protocols; allocate liability to vendors for malfunction; require training and O&M manuals. |